## Overview
VendorPulse — MVP Delivery Tracker
Track build progress against the current in-scope MVP. Update daily/weekly. Keep the team focused; surface drift early.
How to use this workbook
1. The 'Task Tracker' is the main sheet — work the tasks, set Status and % Complete as you go.
2. A module is only 'Done' when every row for it is Done AND its 'Module Exit Criteria' all pass.
3. Log progress each day/week in 'Weekly Progress Log' to track velocity and catch drift early.
4. The current scope is the MVP baseline ('MVP Scope'). Anything new from the discovery phase goes
into 'Scope Change Log' first — decide in/out before it touches the plan. Don't silently expand scope.
5. 'Dashboard' auto-summarises status and % complete by area (formulas).
6. Status values: Not Started, In Progress, In Review, Blocked, Done (colour-coded in Task Tracker).
Legend — Status colours
Done
In Progress
In Review
Blocked
Not Started
Sheets
• MVP Scope — what is in / out of the MVP baseline
• Milestones — phase/week plan with status
• Task Tracker — granular tasks + Definition of Done (main sheet)
• Module Exit Criteria — the gate checklist to call a module done
• Weekly Progress Log — running progress log
• Scope Change Log — discovery-phase changes vs the baseline
• Dashboard — auto summaries

## MVP Scope
MVP Scope Baseline
This is the agreed MVP. Treat it as the frozen target. New asks go through Scope Change Log.
Category | In scope (MVP) | Out of scope / later
Workflow | 12-state forward-only WorkflowEngine; all 6 modules A–F | Parallel/branching workflows; multi-cycle batch ops
Module A — Scheduling | Attendee refresh, availability, deterministic slot ranking, invite + Teams meeting after approval, RSVP | Auto-rescheduling; external attendee self-service
Module B — Scorecard | Native in-app form, distribution via Graph mail, deterministic validation + compile + outliers | Third-party survey tools; weighted scoring config UI
Module C — Alignment | AI draft action items + score-change summary, human-approved | Auto-assignment of actions to owners
Module D — Vendor Prep | AI vendor brief + 3 response options per pushback, human-approved | Vendor-facing portal
Module E — Meeting | Transcript parse, AI minutes, send after approval, Blob storage | Live in-meeting transcription; real-time copilots
Module F — Analytics | Deterministic trends/trajectories + AI leadership brief card | Predictive forecasting; cross-tenant benchmarking
AI | Single in-house AI Service -> Azure AI Foundry GPT-4o (in-tenant), draft text only, behind approval gate | MAF SDK (removed); agentic multi-step autonomy; Anthropic/other LLMs
Identity | Entra SSO (OIDC) + RBAC (Coordinator/Sponsor/Viewer); Graph app-only certificate | Guest/B2B external identities
Hosting | 2 Azure VMs in Private VNet; App Gateway + WAF (Front Door removed) | Container Apps / Foundry Hosted Agents (future)
Data | PostgreSQL Flexible Server (system of record); Blob for files; KV for secrets | Data warehouse / BI export; pgvector RAG
Observability | App Insights + Log Analytics via OpenTelemetry; immutable audit | Custom SIEM integration
Integrations | Microsoft Graph (Mail.Send, Calendars.ReadWrite, OnlineMeetings) | Non-Microsoft mail/calendar
Admin | Admin module, Shell branding, Outlook templates | Self-service tenant onboarding

## Milestones
Milestones / Phase Plan
High-level phases. Fill target dates and update status as you go.
Phase | Key outcomes | Target date | Status | % Complete | Notes
Phase 0 — Pre-mobilisation | Shell provisions Entra app regs + admin consent, service mailbox, Azure infra, DNS/TLS, repo + CI/CD; LLM provider confirmed |  | Not Started | 0%
Week 1 — Foundations & migration | JSON->Postgres, Key Vault, remove Google, Entra SSO+RBAC, Graph cert, Module A live, design freeze |  | Not Started | 0%
Week 2 — Development | All modules built, scorecard, branding, Outlook templates, admin module, code freeze |  | Not Started | 0%
Week 3 — Stabilisation & UAT | Hardening, UAT by Shell VMO, observability + runbook, defect fixes, release readiness |  | Not Started | 0%
Week 4 — Deployment & warranty | IT Security sign-off, CAB, prod cutover & go-live, pilot cycle, training, warranty begins |  | Not Started | 0%
Parallel — Compliance | AI Registry/IAQ, EU AI Act classification, Shell.AI + TRB approval (external lead time) |  | Not Started | 0% | Must clear before prod

## Task Tracker
Task Tracker
The main sheet. Each row has a Definition of Done. Set Status + % as you progress. Filter by Area.
Area | ID | Task / Deliverable | Definition of Done (acceptance criteria) | Owner | Est (d) | Status | % Complete | Start | Target | Actual done | Notes / Blockers
Foundations | FND-1 | Provision 2 Azure VMs in Private VNet (IaC: Bicep/Terraform) | Both VMs deployed via IaC; VNet-private; reproducible; peer-reviewed |  | 2 | Not Started | 0%
Foundations | FND-2 | Application Gateway + WAF (OWASP), origin-lock, TLS | Only App Gateway reaches the VMs; OWASP rules on; TLS terminated; backend has no public IP |  | 1 | Not Started | 0%
Foundations | FND-3 | PostgreSQL Flexible Server (VNet-private, SSL) | DB reachable only inside VNet; SSL enforced; credentials stored in Key Vault |  | 1 | Not Started | 0%
Foundations | FND-4 | JSON/SQLite -> PostgreSQL migration (BaseRepository seam) | All entities persist to Postgres; repository seam swapped; no file persistence; data integrity verified |  | 2 | Not Started | 0%
Foundations | FND-5 | Key Vault + Managed Identity | All secrets (LLM key, Graph cert, JWT key, DB creds) in KV; fetched via MI at runtime; no secrets in code/.env in deployed envs |  | 1 | Not Started | 0%
Foundations | FND-6 | Entra SSO (OIDC) + JWT validation | Login via Shell Entra; every protected route validates JWT against well-known config; unauthenticated requests rejected |  | 1.5 | Not Started | 0%
Foundations | FND-7 | RBAC (Coordinator / Sponsor / Viewer) from token claims | Roles enforced server-side; UI reflects role; Viewer cannot mutate state |  | 1 | Not Started | 0%
Foundations | FND-8 | Graph app-only certificate auth (MSAL, mailbox-scoped) | App authenticates with cert from KV; Application Access Policy limits to service mailbox; token auto-refresh |  | 1.5 | Not Started | 0%
Foundations | FND-9 | Remove Google / Gmail / Forms components | No Google packages or config remain; functions moved to Graph + native form |  | 0.5 | Not Started | 0%
Foundations | FND-10 | App Insights + OpenTelemetry instrumentation | Traces/metrics/logs emitted via OTel; correlation IDs link HTTP <-> service <-> model; immutable audit trail |  | 1 | Not Started | 0%
Foundations | FND-11 | Egress proxy configuration on VM2 (HTTP(S)_PROXY) | All outbound (Graph, Foundry) routed via Shell egress; no direct internet egress |  | 0.5 | Not Started | 0%
Foundations | FND-12 | WorkflowEngine (12-state, forward-only) verified/ported | Invalid transitions raise error -> 409; single source of truth; unit-tested across all 12 states |  | 1 | Not Started | 0%
Foundations | FND-13 | Approval gate (HITL) framework | AI outputs flagged requires_approval; external actions fire only from deterministic route post-approval; agent has no side-effect tool |  | 1.5 | Not Started | 0%
Foundations | FND-14 | AI Service (Azure AI Foundry GPT-4o; MAF removed) | AI Service wraps Foundry via Azure OpenAI SDK; in-tenant; returns drafted text only; structured output validated |  | 1.5 | Not Started | 0%
Foundations | FND-15 | AgentResponse contract + adapter | Single response shape for AI and deterministic paths; frontend depends on it; both paths emit identical envelope |  | 1 | Not Started | 0%
Foundations | FND-16 | CI/CD pipeline (build, lint, SAST/dep/secret scan, deploy) + regression tests | Pipeline gates deploys; scans pass; regression covers approval gate, deterministic path, AgentResponse; prod needs manual approval |  | 2 | Not Started | 0%
Module A — Scheduling | A1 | Cycle creation (route + repo, state CYCLE_CREATED) | Cycle created, persisted; state set via WorkflowEngine |  | 1 | Not Started | 0%
Module A — Scheduling | A2 | Attendee refresh (Graph User.Read.All) | Attendee list pulled/refreshed; state ATTENDEE_REFRESH_SENT |  | 1 | Not Started | 0%
Module A — Scheduling | A3 | Availability collection (Graph calendar free/busy) | Availability gathered for attendees; state AVAILABILITY_COLLECTED |  | 1 | Not Started | 0%
Module A — Scheduling | A4 | Deterministic slot ranking | Slots ranked by deterministic algorithm; reproducible; no LLM |  | 1 | Not Started | 0%
Module A — Scheduling | A5 | AI Service: polish invite text (optional) | Draft invite generated; requires_approval; deterministic fallback text when LLM off |  | 0.5 | Not Started | 0%
Module A — Scheduling | A6 | Approval + send invites (Graph Calendars.ReadWrite, OnlineMeetings) | Invite/Teams meeting created only after human approval, from deterministic route; state MEETING_SCHEDULED |  | 1.5 | Not Started | 0%
Module A — Scheduling | A7 | RSVP status tracking | RSVP statuses read from Graph and surfaced in UI |  | 0.5 | Not Started | 0%
Module A — Scheduling | A8 | Frontend Scheduling module + ApprovalPanel + progress bar | UI drives Module A end to end; role-gated; reflects workflow state |  | 1.5 | Not Started | 0%
Module B — Scorecard | B1 | Scorecard request distribution (native form magic-link via Graph mail) | Requests sent to stakeholders; state SCORECARD_REQUEST_SENT |  | 1 | Not Started | 0%
Module B — Scorecard | B2 | Native in-app scorecard form (React) + SSO / one-time token | Internal via SSO, external via one-time token; submissions validated |  | 1.5 | Not Started | 0%
Module B — Scorecard | B3 | Collection + polling / status | Submissions tracked; state SCORECARD_COLLECTION |  | 0.5 | Not Started | 0%
Module B — Scorecard | B4 | Deterministic validation | All scores validated by rules; invalid rejected; no LLM |  | 1 | Not Started | 0%
Module B — Scorecard | B5 | Compile + outlier detection (deterministic) | Compiled scorecard; outliers flagged deterministically; state SCORECARD_COMPILED |  | 1 | Not Started | 0%
Module B — Scorecard | B6 | Frontend Scorecard module + status dashboard | Coordinator sees collection status; compiled view renders |  | 1 | Not Started | 0%
Module C — Alignment | C1 | AI Service: extract action items from notes | Draft action items; requires_approval; grounded in notes; audited |  | 1 | Not Started | 0%
Module C — Alignment | C2 | AI Service: summarise score changes | Draft summary grounded in compiled scorecard; requires_approval |  | 1 | Not Started | 0%
Module C — Alignment | C3 | Approval gate integration | AI outputs approved before use; deterministic fallback available |  | 0.5 | Not Started | 0%
Module C — Alignment | C4 | Frontend Alignment module | UI shows/edits/approves; state INTERNAL_ALIGNMENT |  | 1 | Not Started | 0%
Module D — Vendor Prep | D1 | AI Service: generate vendor brief | Draft brief grounded in cycle data; requires_approval; audited |  | 1 | Not Started | 0%
Module D — Vendor Prep | D2 | AI Service: draft 3 response options per pushback | 3 distinct options per pushback; requires_approval |  | 1 | Not Started | 0%
Module D — Vendor Prep | D3 | Approval gate integration | Brief and responses approved before they can be shared |  | 0.5 | Not Started | 0%
Module D — Vendor Prep | D4 | Frontend Vendor Prep module | UI renders brief + options; state VENDOR_PREP |  | 1 | Not Started | 0%
Module E — Meeting | E1 | AI Service: parse transcript | Transcript parsed into structured notes; requires_approval |  | 1 | Not Started | 0%
Module E — Meeting | E2 | AI Service: generate meeting minutes | Draft minutes; requires_approval; grounded in transcript |  | 1 | Not Started | 0%
Module E — Meeting | E3 | Blob storage for transcripts / minutes (immutable) | Stored append-only; retrievable; never updated/deleted |  | 0.5 | Not Started | 0%
Module E — Meeting | E4 | Approval + send minutes (Graph Mail.Send) | Minutes sent only after approval; state MEETING_IN_PROGRESS -> POST_MEETING_COMPLETE |  | 1 | Not Started | 0%
Module E — Meeting | E5 | Frontend Meeting module | UI captures meeting, shows minutes, drives state |  | 1 | Not Started | 0%
Module F — Analytics | F1 | Deterministic analytics (vendor trajectories / trends) | Computed deterministically from cycle history; reproducible |  | 1 | Not Started | 0%
Module F — Analytics | F2 | AI Service: leadership brief card | Draft brief card; requires_approval; audited |  | 1 | Not Started | 0%
Module F — Analytics | F3 | Frontend Analytics page + charts (Recharts) | Dashboards render per completed cycle; charts correct |  | 1 | Not Started | 0%
Admin & Branding | ADM-1 | Admin module (user/role management, cycle config) | Admin can manage roles/config; RBAC-gated to admin role |  | 1.5 | Not Started | 0%
Admin & Branding | ADM-2 | Shell branding applied | Branding consistent across all UI via Design System |  | 0.5 | Not Started | 0%
Admin & Branding | ADM-3 | Outlook email templates configured | Templates used for invites and minutes; render correctly in Outlook |  | 0.5 | Not Started | 0%
Deployment & Go-Live | DEP-1 | Staging environment + smoke tests | Staging deployed; automated smoke tests pass |  | 1 | Not Started | 0%
Deployment & Go-Live | DEP-2 | Hardening & stabilisation | UAT defects fixed; performance acceptable; error handling verified |  | 2 | Not Started | 0%
Deployment & Go-Live | DEP-3 | UAT with Shell VMO team | All UAT scenarios executed and signed off by Shell |  | 2 | Not Started | 0%
Deployment & Go-Live | DEP-4 | Observability dashboards + runbook | Dashboards live in App Insights; operational runbook documented |  | 1 | Not Started | 0%
Deployment & Go-Live | DEP-5 | IT Security sign-off | Shell IT Security review passed |  | 1 | Not Started | 0%
Deployment & Go-Live | DEP-6 | CAB approval | Change Advisory Board approval obtained |  | 0.5 | Not Started | 0%
Deployment & Go-Live | DEP-7 | Production cutover & go-live | Prod live; pilot vendor cycle kicked off |  | 1 | Not Started | 0%
Deployment & Go-Live | DEP-8 | Coordinator training & handover | Training delivered; handover docs complete |  | 1 | Not Started | 0%
Deployment & Go-Live | DEP-9 | Defect-warranty support | Warranty period active; defect process agreed |  | 0 | Not Started | 0%
Compliance (Shell) | CMP-1 | AI Registry + ServiceNow registration | System registered in AI Registry / ServiceNow |  | 0 | Not Started | 0%
Compliance (Shell) | CMP-2 | IRM risk assessment / IAQ | IRM IAQ completed and accepted |  | 0 | Not Started | 0%
Compliance (Shell) | CMP-3 | EU AI Act classification | Risk classification completed and recorded |  | 0 | Not Started | 0%
Compliance (Shell) | CMP-4 | Shell.AI + TRB model/design approval | Model and design approved by Shell.AI and TRB |  | 0 | Not Started | 0%
Compliance (Shell) | CMP-5 | Entra app registrations (NonProd+Prod) + admin consent | App regs created; admin consent granted on Graph permissions |  | 0 | Not Started | 0%
Compliance (Shell) | CMP-6 | Service mailbox + Application Access Policy | Service mailbox provisioned; access policy scoped to the app |  | 0 | Not Started | 0%
Compliance (Shell) | CMP-7 | DNS hostnames + TLS certificates | Prod/NonProd hostnames and TLS certs provisioned |  | 0 | Not Started | 0%

## Module Exit Criteria
Module Exit Criteria (Definition of Done)
A module is DONE only when ALL its criteria are met. Generic criteria apply to every module.
Scope | Exit criterion (must be true to call it done) | Met? (Y/N) | Evidence / notes
ALL MODULES (generic)
State transitions enforced only via WorkflowEngine (invalid -> 409)
Deterministic path works with ENABLE_LLM=false (where the module uses AI)
All AI outputs pass through the approval gate — no auto-send
AgentResponse contract honoured by both AI and deterministic paths
Every run audited with correlation IDs (OTel -> App Insights)
RBAC enforced server-side for the module's actions
Unit + regression tests pass in CI
No secrets in code; all via Key Vault + Managed Identity
Module UAT scenario executed and signed off by Shell VMO
Module A — Scheduling
Invite + Teams meeting created only after approval, from deterministic route
Slot ranking is deterministic and reproducible (no LLM)
Cycle reaches MEETING_SCHEDULED only through the valid state path
Module B — Scorecard
All scorecards validated deterministically; no LLM in the data path
Compile + outlier detection reproducible; SCORECARD_COMPILED reached
Module C — Alignment
Action items + score-change summary are drafts, human-approved before use
Module D — Vendor Prep
Brief + exactly 3 response options per pushback; approved before share
Module E — Meeting
Minutes sent only after approval; transcript/minutes stored immutably in Blob
POST_MEETING_COMPLETE reached only via the valid path
Module F — Analytics
Analytics computed deterministically from history; brief card approved

## Weekly Progress Log
Weekly / Daily Progress Log
One row per update. Track what shipped, overall %, blockers, and the next focus — to catch drift early.
Week / Period | Date | Focus (area/module) | Done this period | % overall | Blockers / risks | Decisions | Next focus | Updated by

## Scope Change Log
Scope Change Log (vs MVP baseline)
Discovery-phase or later changes land here first. Decide In MVP / Defer / Reject before touching the plan.
Change ID | Date raised | Raised by | Description | Type | In MVP? | Impact (scope/time/cost) | Decision | Approved by | Date decided

## Dashboard
Dashboard (auto)
Summaries computed from the Task Tracker. Refreshes when you edit it.
Overall % complete
Tasks by status | % complete by area
Done | Foundations
In Progress | Module A — Scheduling
In Review | Module B — Scorecard
Blocked | Module C — Alignment
Not Started | Module D — Vendor Prep
Total tasks | Module E — Meeting
Module F — Analytics
Admin & Branding
Deployment & Go-Live
Compliance (Shell)