## Implementation Plan
VendorPulse - EGB / QBR Process Automation
CLIENT Implementation Plan - 4-week delivery overview, dependencies & key dates
Phase 0 pre-mobilisation readiness window from Thu 18-Jun-2026 ¦ T-0 = Mon 22-Jun-2026 ¦ 4 working weeks (20 days): Wk1 22-26 Jun ¦ Wk2 29 Jun-3 Jul ¦ Wk3 6-10 Jul ¦ Wk4 13-17 Jul (deployment & warranty) ¦ CR-9 EGB
Reading guide: Phase 0 is Shell-side readiness, confirmed in the 18-19 Jun window before the Mon 22-Jun (T-0) start - 'HARD by T-0' items must be ready on the start date. The two long-lead items (Graph admin consent, LLM contract/DPA) must be INITIATED ~4-6 weeks earlier. Gates are shown in gold; orange = hard Day-1 prerequisite.
Team (Zensar): 1 Delivery Mgr, 1 Solution Architect, 1 Tech Lead, 2 Backend, 2 Frontend, 1 QA, 1 DevOps - 100% allocated, no planned leave Wk1-3. Scope basis: the proven POC behaviour (Modules A-F) is the baseline; this engagement re-platforms it onto Shell-grade Azure - it does not rebuild the features. New functional requirements are out of scope and re-estimated.
Sr | Phase | Activity | Start | Days | End | Depends On | Needed By | Outcome / Notes
PHASE 0 - Pre-Mobilisation - Shell readiness, confirmed in the 18-19 Jun window before the 22-Jun start (long-lead items initiated 4-6 weeks earlier)
1 | P0 | Identity & single sign-on | 2026-06-18 | 2 | 2026-06-19 | - | HARD by T-0 (22-Jun) | Entra app registrations with certificate credentials, OIDC single sign-on, and security groups for the 4 roles (VMO coordinator, admin, executive sponsor, viewer).
2 | P0 | Microsoft Graph admin consent (LONG POLE) | 2026-06-18 | 2 | 2026-06-19 | App registrations | Initiated ~4-6 wks early; clears by end Wk1 (26-Jun) | A 2-4 week Shell security review - the single biggest schedule risk - so it must be started weeks before mobilisation. Needed for Module A on real Graph by Friday of Week 1.
3 | P0 | Service mailbox & least-privilege policy | 2026-06-18 | 2 | 2026-06-19 | - | HARD by T-0 (22-Jun) | Dedicated vendorpulse-svc mailbox (E3/E5 licence) plus the Exchange Application Access Policy that confines the service to that one mailbox.
4 | P0 | Teams & external-attendee policies | 2026-06-18 | 2 | 2026-06-19 | Service mailbox | By Wk1 (decision); pilot by Wk4 | Teams meeting-creation policy for the service mailbox, and confirmation it may invite external (vendor) attendees. Email-render QA account (Litmus) for Day-8 template checks.
5 | P0 | Azure compute, data & secrets | 2026-06-18 | 2 | 2026-06-19 | Subscription | HARD by T-0 (22-Jun) | Subscription + nonprod/prod resource groups, App Service + Container Registry, PostgreSQL Flexible Server, and Key Vault - the platform the application is built on.
6 | P0 | Networking, connectivity & egress | 2026-06-18 | 2 | 2026-06-19 | Subscription | HARD by T-0 (DNS/TLS by Wk4) | Front Door + WAF, private endpoints, the outbound egress allow-list to Graph + the AI endpoints, and App Insights. Public DNS + TLS are needed for the Week-4 cutover, not Day 1.
7 | P0 | LLM provider contract + DPA (LONG POLE) | 2026-06-18 | 2 | 2026-06-19 | - | Decided by T-0; initiated ~4-6 wks early; key for Wk2 | A 4-8 week contract/DPA - Anthropic Claude recommended (zero-retention, no-training, EU-residency); Azure OpenAI a config-only alternative. Powers the AI text in Modules C-F.
8 | P0 | Source control, CI/CD & engineer access | 2026-06-18 | 2 | 2026-06-19 | Subscription | HARD by T-0 (22-Jun) | VPN / device-compliance access to the tenant, repo and non-prod Graph (a frequently-underestimated long pole), and the source-control + CI/CD platform with Zensar engineers onboarded as guests.
9 | P0 | Zensar delivery tooling | 2026-06-18 | 2 | 2026-06-19 | - | HARD by T-0 (22-Jun) | Engineer laptops with a full local environment + admin rights, an approved IDE, and Claude Code / Claude for Work licences - the AI-assisted velocity the 4-week plan depends on.
10 | P0 | Legal / Privacy sign-off path | 2026-06-18 | 2 | 2026-06-19 | LLM DPA | Go-live precondition (Wk4) | Data-residency and audit-retention sign-off path agreed (the audit log holds vendor names + scorecard comments). Started early alongside the DPA.
11 | P0 | People named & key decisions locked | 2026-06-18 | 2 | 2026-06-19 | - | HARD by T-0 (22-Jun) | Product Owner/VMO lead, liaisons, admins and 3 UAT coordinators named; pre-Day-1 decisions locked (provider, region, mailbox name + display name, database + CMK, CI/CD platform, vendor-master format, external-attendee policy).
PHASE 1 - Week 1 (22-26 Jun) - Foundations, Migration & Design Alignment
12 | P1 | Secure the platform | 2026-06-22 | 2 | 2026-06-23 | Azure platform; CI/CD (P0) | Days 1-2 | Branch the code and scrub POC secrets from history; wire Key Vault + Managed Identity so no secrets live in code or config. Day-1 connectivity smoke-tests.
13 | P1 | Migrate data to Azure PostgreSQL | 2026-06-22 | 4 | 2026-06-25 | PostgreSQL provisioned (P0) | Days 1-4 | Move the flat JSON / SQLite data into a managed PostgreSQL database (~15 tables) - the production system of record for workflow state, scores and audit.
14 | P1 | Remove the Google / Gmail / Forms stack | 2026-06-22 | 3 | 2026-06-24 | Branch created | Days 1-3 | The consumer Google stack used in the POC is removed entirely; everything moves to Microsoft 365 (Graph, Teams, Outlook).
15 | P1 | Connect Microsoft Graph (secure auth) | 2026-06-23 | 4 | 2026-06-26 | Admin consent; mailbox (P0) | Days 2-5 | GraphService re-platformed onto app-only certificate authentication from the service mailbox - no pasted tokens.
16 | P1 | Entra single sign-on & role-based access | 2026-06-23 | 4 | 2026-06-26 | Entra SSO + groups (P0) | Days 2-5 | Users sign in with their Shell identity; the four roles are enforced on the server, never in the browser.
17 | P1 | Wire the AI provider | 2026-06-24 | 2 | 2026-06-26 | LLM key (P0) | Days 3-5 | Provider-abstracted LLM (Anthropic Claude recommended; Azure OpenAI a config-only switch). Agent layer is self-built tool-calling - no MAF SDK. AI is optional and never blocks the workflow.
18 | P1 | Day-2 Design Alignment Checkpoint [GATE] | 2026-06-23 | 1 | 2026-06-23 | Decisions locked (P0) | GATE - Day 2 (23-Jun) | Lock ~12 design decisions: scorecard mechanism & the 4-category/16-parameter taxonomy (Risk & Compliance, Performance, Commercial, Relationship), brief/minutes formats, vendor-master source, approval routing.
19 | P1 | Module A live on real Graph | 2026-06-24 | 3 | 2026-06-26 | Graph admin consent; mailbox (P0) | By Fri (Day 5) | Scheduling & Coordination end-to-end on real Graph: roster refresh, find times, deterministic slot ranking, Teams meeting + invite, RSVP tracking.
20 | P1 | Design freeze [GATE] | 2026-06-26 | 1 | 2026-06-26 | Module A demo | GATE - Day 5 (26-Jun) | Scope frozen; later changes route to the defect or Phase-2 path.
PHASE 2 - Week 2 (29 Jun-3 Jul) - Functional Build
21 | P2 | Scorecard module (B) | 2026-06-29 | 4 | 2026-07-02 | Taxonomy locked (Day 2) | Days 6-10 | Native in-app scorecard form (1-5 across 4 categories / 16 parameters); deterministic validation and outlier flagging; requests + escalating reminders via Outlook. Approval gate on the emails.
22 | P2 | Alignment (C) & Vendor Prep (D) | 2026-06-29 | 4 | 2026-07-02 | LLM key; Graph (P0) | Days 6-10 | Score-change narrative and action items; internal Teams alignment meeting; AI vendor brief and three response stances per pushback (AI suppressed on legal-review items).
23 | P2 | Meeting (E) & Cross-Cycle Trends (F) | 2026-06-29 | 4 | 2026-07-02 | LLM key; Postgres | Days 6-10 | Facilitator briefing, transcript-to-minutes, action items, and minutes distribution via Outlook; multi-cycle trends, recurring-issue detection and the executive leadership brief.
24 | P2 | Shell-branded user interface | 2026-06-29 | 3 | 2026-07-01 | Brand assets (P0) | Days 6-8 | Shell branding applied across the web app; the approval panel is the primary review surface for every AI draft.
25 | P2 | Outlook email templates + render QA | 2026-06-29 | 4 | 2026-07-02 | Brand sign-off by Day 8 (P0) | Day 8 (brand) / Day 10 | Outlook-friendly templates verified on Outlook desktop, OWA and mobile via cross-client QA.
26 | P2 | Admin module, audit trail & accessibility | 2026-06-29 | 4 | 2026-07-02 | App Insights (P0) | Days 6-10 | Admin views (vendor master, roles, AI budget, audit-log viewer, system health); append-only audit trail with approver attribution; automated accessibility checks.
27 | P2 | Initial hardening | 2026-07-01 | 3 | 2026-07-03 | All modules | Days 8-10 | Rate limiting, AI token-budget guards, retry/backoff and end-to-end correlation IDs (completed before the mid-Wk3 code freeze).
28 | P2 | All six agents functional (milestone) | 2026-07-03 | 1 | 2026-07-03 | Modules A-F | End of Wk2 (3-Jul) | Functional build substantially complete; remaining completion + final hardening carry into early Wk3, up to the Day-13 code freeze.
PHASE 3 - Week 3 (6-10 Jul) - Completion, mid-week Code Freeze (Wed 8-Jul), Stabilisation & UAT (no go-live)
29 | P3 | Final completion & hardening | 2026-07-06 | 3 | 2026-07-08 | Functional build (Wk2) | Days 11-13 (by code freeze) | Close out any remaining build and finish hardening ahead of the mid-week code freeze.
30 | P3 | UAT with 3 named VMO coordinators | 2026-07-06 | 5 | 2026-07-10 | Modules functional; coordinators (P0) | Days 11-15 | Risk-based testing across all six modules; begins on completed modules and intensifies after the code freeze (defect fixes only thereafter).
31 | P3 | Defect triage & daily burn-down | 2026-07-06 | 5 | 2026-07-10 | UAT | Days 11-15 | P1 resolved same-day; P1/P2 closed before sign-off; P3 triaged to warranty/Phase 2.
32 | P3 | Observability, alerting & runbook v1.0 | 2026-07-06 | 5 | 2026-07-10 | App Insights (P0) | Days 11-15 | Operational readiness for handover to Shell IT Ops.
33 | P3 | Code freeze [GATE] | 2026-07-08 | 1 | 2026-07-08 | All modules functional; hardening done | GATE - Day 13 (Wed 8-Jul) | Middle of Week 3. No further feature development; stabilisation & defect fixes only from here.
34 | P3 | Regression & smoke testing | 2026-07-08 | 3 | 2026-07-10 | Code freeze | Days 13-15 (post-freeze) | Confirms the deterministic core (slot ranking, score validation, workflow transitions) behaves identically after re-platforming.
35 | P3 | Validate platform capabilities | 2026-07-08 | 3 | 2026-07-10 | Audit; RBAC; Graph auth | Days 13-15 (post-freeze) | Audit append-only behaviour, role-based access, secure Graph auth and email rendering all verified before cutover.
36 | P3 | UAT sign-off [GATE] | 2026-07-10 | 1 | 2026-07-10 | Defects closed | GATE - Day 15 (10-Jul) | All P1/P2 UAT defects closed; release candidate approved for deployment.
PHASE 4 - Week 4 (13-17 Jul) - Security Sign-off, Deployment & Defect-Warranty
37 | P4 | Shell IT Security review & sign-off [GATE] | 2026-07-13 | 2 | 2026-07-14 | UAT sign-off | GATE - early Wk4 | Sign-off on Graph scopes, Application Access Policy, RBAC and audit posture before cutover.
38 | P4 | Confirm production prerequisites | 2026-07-13 | 2 | 2026-07-14 | DNS/TLS, CA path, Front Door (P0) | Before cutover | Production DNS + TLS, Conditional Access path for the service principal, Front Door/WAF prod config; pilot vendor-master (CSV/Excel) imported.
39 | P4 | CAB approval & production cutover [GATE] | 2026-07-14 | 2 | 2026-07-15 | Security sign-off | GATE - Wk4 (Wed-Thu) | Change Advisory Board approval; go-live via DNS change + slot-swap with a 60-minute observation window and tested rollback.
40 | P4 | Pilot cycle kick-off & handover [GATE] | 2026-07-16 | 2 | 2026-07-17 | Cutover; vendor-master | Wk4 (Thu-Fri) | One real pilot vendor cycle kicked off in production (Tech Lead pair-shadowing); recorded coordinator training; runbook v1.0 + decision log handed over.
41 | P4 | Defect-warranty support begins | 2026-07-17 | 1 | 2026-07-17 | Go-live | From go-live | 4-week warranty: Zensar fixes P1/P2 (P1 same-day where feasible) while Shell runs BAU; warranty dates agreed in writing at handover.
Key Dates & Gates
Milestone | Date | Meaning
T-0 / Day 1 | Mon 22-Jun-2026 | Engagement start - all HARD Day-1 prerequisites in place
Day-2 checkpoint [GATE] | Tue 23-Jun | ~12 design decisions locked
Design freeze [GATE] | Fri 26-Jun | Module A live on real Graph; scope frozen
All six agents functional | Fri 3-Jul | End of Week 2 build milestone (not a gate)
Code freeze [GATE] | Wed 8-Jul | Middle of Week 3; no further feature development - stabilisation only
UAT sign-off [GATE] | Fri 10-Jul | P1/P2 defects closed; release candidate approved
Security sign-off [GATE] | Mon-Tue 13-14 Jul | Shell IT Security approval
CAB approval & cutover [GATE] | Wed-Thu 15-16 Jul | Go-live via DNS + slot-swap; pilot cycle kick-off
Handover [GATE] | Fri 17-Jul | Training, runbook v1.0, decision log handed over; warranty begins
Out of Scope (this release)
- Shell-wide vendor master / SAP Ariba / Coupa integration - the pilot vendor list is seeded from CSV/Excel; system integration is a follow-on phase.
- Contract-management feature - contract terms are referenced for context only, not stored or analysed.
- Finance / spend / SAP integration - spend figures are referenced manually within scorecards.
- Mobile native app (web-only, desktop browser) and multi-language UI (English only at launch).
- Microsoft Teams transcript ingestion - transcripts are pasted in for parsing at launch.
- Deferred to warranty / Phase 2: performance & load testing, third-party penetration test, formal manual WCAG audit, comprehensive automated regression suite, multi-vendor onboarding, cross-region DR, customer-managed keys (CMK).
Assumptions (the plan holds only if...)
- Shell completes all pre-mobilisation access before Day 1; the two long-lead items (Graph admin consent, LLM contract/DPA) are initiated 4-6 weeks ahead, during contract negotiation.
- The Zensar team is 100% allocated with no planned leave across Weeks 1-3 (deployment & warranty in Week 4).
- AI-assisted delivery tooling (laptops + admin rights, approved IDE, Claude Code licences) is available to every engineer from Day 1 - the velocity the 4-week plan depends on.
- The proven POC behaviour (Modules A-F) is accepted as the baseline; this engagement re-platforms it, it does not rebuild the features. New functional requirements are out of scope and re-estimated.
- One pilot vendor cycle, with its vendor-master data provided in time for the Week-4 kick-off; the service mailbox may invite external (vendor) attendees.
- Design is frozen at the end of Week 1 and code in the middle of Week 3 (Wed 8-Jul); later changes follow the defect or Phase-2 path.
- Launch is English-only, web-only (desktop browser) and single-tenant (Shell only); platform-managed encryption keys (CMK deferred).