## Implementation Plan
VendorPulse - EGB / QBR Process Automation
DETAILED Implementation Plan - full task breakdown, dependencies, owners & dated milestones
Phase 0 pre-mobilisation readiness window from Thu 18-Jun-2026 ¦ T-0 = Mon 22-Jun-2026 ¦ 4 working weeks (20 days): Wk1 22-26 Jun ¦ Wk2 29 Jun-3 Jul ¦ Wk3 6-10 Jul ¦ Wk4 13-17 Jul (deployment & warranty) ¦ CR-9 EGB
Legend: orange = HARD Day-1 blocker (must be complete by T-0) ¦ gold = quality GATE ¦ Phase 0 is a parallel readiness window dated 18-19 Jun - external lead times are in the Pre-Mob Checklist 'Lead time' column; the two long poles (Graph admin consent, LLM contract/DPA) must be INITIATED ~4-6 wks before T-0. Agent layer = self-implemented tool-calling (no MAF SDK); LLM provider-abstracted (Anthropic Claude recommended, Azure OpenAI config-only).
Team (Zensar, 100% allocated, no planned leave Wk1-3; deployment & warranty Wk4): 1 Delivery Mgr, 1 Solution Architect, 1 Tech Lead, 2 Backend, 2 Frontend, 1 QA, 1 DevOps/Cloud. Shell supporting: Exec Sponsor (~2h/wk), Product Owner/VMO lead (daily), IT Architecture & Security liaisons, Entra/Exchange/Azure admins, DBA, Networking, Procurement, Legal/Privacy, 3 VMO coordinators, Brand/Comms.
Scope basis: POC functional behaviour (Modules A-F) is accepted as the baseline; effort sizes the integration & platform re-engineering only - NOT rework of functional logic, the 12-state workflow, the human-approval gate or the deterministic-first rules. New/changed functional requirements are out of scope and require re-estimation. Launch is English-only, web-only (desktop browser) and single-tenant (Shell's Azure subscription + M365 tenant only).
Architectural invariants (unchanged across A-F): (1) 12-state forward-only workflow - CYCLE_CREATED -> ATTENDEE_REFRESH_SENT -> AVAILABILITY_COLLECTED -> MEETING_SCHEDULED -> SCORECARD_REQUEST_SENT -> SCORECARD_COLLECTION -> SCORECARD_COMPILED -> INTERNAL_ALIGNMENT -> VENDOR_PREP -> MEETING_IN_PROGRESS -> POST_MEETING_COMPLETE -> ARCHIVED (invalid transitions rejected); (2) human-approval gate on every outbound action; (3) deterministic-first, AI-second.
Sr | Phase | Workstream | Task / Deliverable | Start | Days | End | Dependency | Required By / Milestone | Remarks
PHASE 0 - Pre-Mobilisation (before T-0; Shell-led, runs in parallel with contract negotiation. Long-lead items start ~4-6 weeks ahead)
1 | P0 | Identity (Entra ID) | Two app registrations (NonProd + Prod) with certificate-based credentials; cert as Key Vault certificate object; 12-month auto-renewal pipeline | 2026-06-18 | 2 | 2026-06-19 | Azure subscription | HARD Day-1 blocker (T-0) | App-only Graph auth + SSO. Cert Shell-generated (preferred) or Zensar-generated, thumbprint returned. Nothing integration-related can start without it.
2 | P0 | Identity (Entra ID) | Admin consent on Graph application permissions: Mail.Send, Calendars.ReadWrite, OnlineMeetings.ReadWrite.All, User.Read.All, MailboxSettings.Read, Group.Read.All | 2026-06-18 | 2 | 2026-06-19 | App registrations; Application Access Policy (coupled) | By end of Wk1 (Fri 26-Jun) | LONG POLE - 2-4 wk security review; the single largest schedule risk. Start ~4-6 wks ahead. In-app form avoids Mail.Read/ReadWrite (narrower consent). May be in progress on Day 1; non-prod uses mocks/dev scopes meanwhile.
3 | P0 | Identity (Entra ID) | OIDC client + redirect URIs configured for SSO (per environment) | 2026-06-18 | 2 | 2026-06-19 | App registrations | HARD Day-1 blocker (T-0) | Required for any authenticated UI access via Entra SSO.
4 | P0 | Identity (Entra ID) | Entra security groups for the four app roles (VMO coordinator, VMO admin, executive sponsor, viewer) | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (T-0) | RBAC enforcement; role-gated UI and approval routing.
5 | P0 | Identity (Entra ID) | Exchange Application Access Policy scoping Mail.Send / Calendars to the single service mailbox | 2026-06-18 | 2 | 2026-06-19 | Service mailbox | HARD Day-1 blocker (T-0) | Least-privilege constraint; couple with admin consent as one security-review package or tenant-wide consent is likely refused.
6 | P0 | Identity (Entra ID) | Conditional Access exemption (or confirmed sign-in path) for the service principal | 2026-06-18 | 2 | 2026-06-19 | App registrations | PROD by Wk4 (non-prod may bypass) | Otherwise CA silently blocks outbound mail/calendar. Non-prod can use a confirmed sign-in path; required for production at the Wk4 security gate.
7 | P0 | M365 Messaging | Dedicated service mailbox (e.g. vendorpulse-svc@shell.com) with M365 E3/E5 licence | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (T-0) | From-identity for all outbound Graph mail; calendar host for Teams meetings. ~$23 (E3) / ~$57 (E5) per user/month.
8 | P0 | M365 Messaging | Mailbox storage allocation (~10 GB) + retention policy (auto-archive sent items after ~1 year) | 2026-06-18 | 2 | 2026-06-19 | Service mailbox | By Wk1 | Keeps the mailbox un-throttled across cycles; supports audit-trail and retention compliance.
9 | P0 | M365 Messaging | Teams meeting policy permitting the service mailbox to create online meetings via Graph | 2026-06-18 | 2 | 2026-06-19 | Service mailbox | By Wk1 (Module A) | Module A and C meeting creation; OnlineMeetings provisioning.
10 | P0 | M365 Messaging | External / guest meeting-policy confirmation (can the mailbox invite vendor external attendees?) | 2026-06-18 | 2 | 2026-06-19 | Service mailbox | By Wk1 (decision); pilot by Wk4 | If blocked, Module A cannot include vendor (external) attendees in the EGB/QBR.
11 | P0 | M365 Messaging | Litmus / Email-on-Acid account for cross-client email-render QA | 2026-06-18 | 2 | 2026-06-19 | - | By Day 8 (template QA) | ~$99/month. Validates Outlook desktop / OWA / mobile rendering of brand-signed templates.
12 | P0 | Azure Platform | Azure subscription with deploy access for Zensar engineers | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (T-0) | All deployment, IaC, CI/CD. No environment can be stood up without it.
13 | P0 | Azure Platform | Resource groups (nonprod + prod) | 2026-06-18 | 2 | 2026-06-19 | Azure subscription | HARD Day-1 blocker (T-0) | Environment isolation; all resource provisioning.
14 | P0 | Azure Platform | App Service Plan - P1v3 (prod) and B2 (nonprod), Linux containers | 2026-06-18 | 2 | 2026-06-19 | Resource groups | HARD Day-1 blocker (T-0) | Application hosting. ~$220/month (P1v3 prod); B2 nonprod modest.
15 | P0 | Azure Platform | Azure Database for PostgreSQL Flexible Server (HA / zone-redundant for prod) | 2026-06-18 | 2 | 2026-06-19 | Resource groups | HARD Day-1 blocker (T-0) | Target for the Wk1 JSON->Postgres migration; all persistence.
16 | P0 | Azure Platform | Azure Key Vault | 2026-06-18 | 2 | 2026-06-19 | Resource groups | HARD Day-1 blocker (T-0) | Secret storage; Managed-Identity retrieval; certificate object; secret-scrub remediation.
17 | P0 | Azure Platform | Azure Container Registry | 2026-06-18 | 2 | 2026-06-19 | Resource groups | HARD Day-1 blocker (T-0) | Container image build/push for App Service deployment.
18 | P0 | Azure Platform | Azure Front Door + WAF policy | 2026-06-18 | 2 | 2026-06-19 | Resource groups | By Wk1 (cutover in Wk4) | Public ingress, edge protection, TLS termination, cutover slot-swap.
19 | P0 | Azure Platform | App Insights + Log Analytics workspace | 2026-06-18 | 2 | 2026-06-19 | Resource groups | By Wk1 (gate in Wk3) | Observability, alerts, immutable audit trail; feeds the Wk3 observability gate.
20 | P0 | Azure Platform | Private endpoints + VNet integration (Postgres, Key Vault) | 2026-06-18 | 2 | 2026-06-19 | Resource groups; Postgres; Key Vault | HARD Day-1 blocker (T-0) | App cannot retrieve secrets via MI or reach the DB at start-up without it. Smoke-test on Day 1.
21 | P0 | Azure Platform | Managed Identity role assignments (Key Vault Secrets User, Postgres grants, Log Analytics) | 2026-06-18 | 2 | 2026-06-19 | Key Vault; Postgres; Log Analytics | HARD Day-1 blocker (T-0) | Secret-less runtime auth; app start-up.
22 | P0 | Azure Platform | Outbound NAT / egress allow-listing to Microsoft Graph + LLM endpoints (Anthropic / Azure OpenAI) | 2026-06-18 | 2 | 2026-06-19 | VNet | HARD Day-1 blocker (T-0) | HIDDEN LONG POLE (3-7 days). All Graph and LLM calls fail from inside the VNet without it. Validate from non-prod in Wk1.
23 | P0 | Azure Platform | Azure DNS / CNAME + public TLS certificate | 2026-06-18 | 2 | 2026-06-19 | Front Door | By Wk4 (DNS/TLS cutover) | Public hostname for the Wk4 cutover - required in Wk4, not Day 1.
24 | P0 | Azure Platform | Azure Policy / tagging compliance | 2026-06-18 | 2 | 2026-06-19 | Resource groups | HARD Day-1 blocker (T-0) | Deployments must pass governance or resources are rejected/flagged.
25 | P0 | LLM Provider | Anthropic enterprise account + DPA (zero-retention, no-training, EU-residency) + API key in Key Vault + monthly token budget [RECOMMENDED] | 2026-06-18 | 2 | 2026-06-19 | - | Initiate by T-0; key for Wk2 LLM features | LONG POLE - 4-8 wk contract/DPA. Powers all LLM text (Modules C, D, E, F). ~$1,000/month token budget. Provider-abstracted, so choice is reversible by config.
26 | P0 | LLM Provider | OR Azure OpenAI quota approval + gpt-4o-class chat deployment (NOT preview/computer-use) + key in Key Vault [config-only alternative] | 2026-06-18 | 2 | 2026-06-19 | - | Initiate by T-0 | Same LLM features via the alternative provider behind the single LLMProvider abstraction (switch is config-only). 1-3 wk quota; confirm tool-calling-capable gpt-4o-class in West Europe.
27 | P0 | Delivery Tooling | Developer laptops for every engineer - full local env (Python 3.11+, Node.js, Docker Desktop, Git) + admin rights | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (T-0) | All local development and build. Without admin rights, Docker/dependency setup is blocked. Zensar-controlled go/no-go gate.
28 | P0 | Delivery Tooling | Approved IDE - VS Code (or JetBrains) with required extensions | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (T-0) | Engineer productivity; sanctioned toolchain. Zensar-controlled go/no-go gate.
29 | P0 | Delivery Tooling | Claude Code / Claude for Work licences + Anthropic API developer key (AI-assisted development) | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (T-0) | The compressed 20-day plan depends on AI-assisted pair-programming velocity. If absent, the plan slips. 1-2 wks if new.
30 | P0 | Delivery Tooling | Source control + CI/CD platform (Azure DevOps or GitHub Enterprise): engineers added as guests, repo created, branch protection, CI/CD service principal | 2026-06-18 | 2 | 2026-06-19 | Azure subscription | HARD Day-1 blocker (T-0) | Day-1 branch & secret-scrub; all commits, pipelines, deployments. Guest onboarding 3-7 days, can be slow.
31 | P0 | Delivery Tooling | CI quality/security gates: SonarQube/SonarCloud, secret scanning (TruffleHog/GitLeaks), container scanning (Trivy/Snyk), Dependabot/Renovate | 2026-06-18 | 2 | 2026-06-19 | CI/CD platform | By Wk1 (secret-scrub) / Wk4 (sign-off) | Quality and security gates in CI; secret-scrub verification; supports the Wk4 security sign-off.
32 | P0 | Delivery Tooling | Network access / VPN / device-compliance posture to reach Shell's Azure tenant, repo and non-prod Graph | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (T-0) | HIDDEN LONG POLE (5-10 days). If unresolved, engineers cannot work against Shell environments at all.
33 | P0 | Delivery Tooling | (Optional) Playwright cloud / BrowserStack for broader cross-browser UI checks | 2026-06-18 | 2 | 2026-06-19 | - | By Wk3 (best-effort) | Best-effort under the compressed timeline; not a blocker.
34 | P0 | People & Governance | Shell roles NAMED & available: Executive Sponsor (~2h/wk), Product Owner / VMO lead (daily), IT Architecture & IT Security liaisons, Entra/Exchange/Azure admins, DBA, Networking, Procurement, Legal/Privacy, Brand/Comms | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (PO, IT Arch named) | Any unavailable role can stall a dependency on its critical path. PO/VMO lead and IT Architecture liaison are hard Day-1 named blockers.
35 | P0 | People & Governance | 3 named VMO coordinators identified for UAT (active Weeks 3-4) | 2026-06-18 | 2 | 2026-06-19 | - | Named by T-0; active Wk3-4 | Wk3 UAT, Wk4 training & handover, pilot acceptance.
36 | P0 | People & Governance | Pre-Day-1 decisions LOCKED: LLM provider; hosting region; service-mailbox name & email from-identity / display name; DB choice + CMK yes/no; CI/CD platform; vendor-master format (CSV/Excel); external-attendee policy | 2026-06-18 | 2 | 2026-06-19 | - | HARD Day-1 blocker (T-0) | Platform-level decisions must be settled pre-mob so the Day-2 checkpoint only confirms design-level items. CMK deferred; platform-managed keys for pilot.
37 | P0 | People & Governance | Legal/Privacy: PII / data-residency / audit-retention sign-off path agreed (agent_runs holds vendor names + scorecard comments) | 2026-06-18 | 2 | 2026-06-19 | LLM DPA | Go-live precondition (Wk4) | Until sign-off, auditability of agent_runs vs Shell retention/residency is asserted by design. Start with the DPA, 4-8 wks ahead.
PHASE 1 - Week 1 (Days 1-5, 22-26 Jun) - Foundations, Migration & Design Alignment [Development]
38 | P1 | DevOps | Branch from POC; scrub POC secrets from Git history; rotate ALL secrets into Key Vault | 2026-06-22 | 1 | 2026-06-22 | CI/CD repo + Key Vault (P0) | Day 1 | First task. Verified by secret-scanning in CI. No secrets in code/.env thereafter.
39 | P1 | DevOps | Smoke-test Managed-Identity secret retrieval + private-endpoint connectivity to Postgres & Key Vault from non-prod | 2026-06-22 | 1 | 2026-06-22 | Private endpoints + MI roles (P0) | Day 1 | Confirms the secret-less runtime auth path before build starts.
40 | P1 | DevOps | Validate egress allow-list connectivity to Microsoft Graph + LLM endpoints from non-prod | 2026-06-22 | 1 | 2026-06-22 | Egress allow-listing (P0) | Day 1 | De-risks the hidden network long pole early in Week 1.
41 | P1 | Design | Day-2 Design Alignment Checkpoint - lock ~12 decisions: scorecard mechanism (native in-app form), 4-category/16-parameter taxonomy (Risk & Compliance, Performance, Commercial, Relationship), brief/minutes output formats, vendor-master source, approval routing | 2026-06-23 | 1 | 2026-06-23 | Pre-Day-1 decisions locked (P0) | GATE - Day 2 (Tue 23-Jun) | Confirms design-level items only; platform-level decisions assumed already locked. Taxonomy supersedes the POC's 5-category interim set.
42 | P1 | Backend | Design PostgreSQL schema (~15 tables, Alembic) and migrate flat JSON/SQLite persistence (asyncpg); data cleansing + defaults for missing fields | 2026-06-22 | 4 | 2026-06-25 | Postgres provisioned (P0); Day-2 taxonomy | Days 1-4 | ~13 POC entities -> ~15 tables. Additive-only migrations after the Day-13 code freeze.
43 | P1 | Backend | Wire Azure Key Vault with Managed Identity for runtime secret retrieval across all services | 2026-06-22 | 2 | 2026-06-23 | Key Vault + MI roles (P0) | Days 1-2 | No secrets in configuration files or source control.
44 | P1 | Backend | Remove all Google / Gmail / Google-Forms code entirely from codebase and runtime | 2026-06-22 | 3 | 2026-06-24 | Branch created | Days 1-3 | Acceptance criterion: Google stack fully removed.
45 | P1 | Backend | Refactor GraphService to app-only certificate authentication (MSAL client-credentials, /users/{id} endpoints, retry/backoff on 429/5xx) | 2026-06-23 | 4 | 2026-06-26 | App reg + cert (P0); admin consent for live test | Days 2-5 | Replaces the POC's pasted delegated bearer token. Dev against mocks/dev scopes until consent clears by Friday.
46 | P1 | Backend / Auth | Implement Entra ID OIDC Single Sign-On + RBAC (VMO coordinator, VMO admin, executive sponsor, viewer); server-side enforcement | 2026-06-23 | 4 | 2026-06-26 | OIDC client + security groups (P0) | Days 2-5 | Roles carried in the token; UI reflects role, never decides it.
47 | P1 | AI Platform | Implement LLMProvider abstraction; add recommended Anthropic Claude provider (Azure OpenAI gpt-4o-class config-only alternative). Self-implemented tool-calling agent layer - MAF SDK NOT used. LLM features disable-by-configuration (feature flag); graceful degradation if provider unavailable | 2026-06-24 | 2 | 2026-06-26 | LLM key in Key Vault (P0); egress | Days 3-5 | Switching providers is config-only. Agents use the model's tool-calling for schema-validated structured output. Graceful degradation: the deterministic workflow proceeds if the LLM is down - AI text is optional, never blocking; coordinators can proceed manually.
48 | P1 | Module A | Module A (Scheduling & Coordination) end-to-end on REAL Graph: attendee/roster refresh, findMeetingTimes against real Shell mailboxes, deterministic slot ranking (organiser + sponsor free = hard constraint; soft scoring on attendance %, calendar conflicts, timezone fit), Teams meeting + invite, RSVP tracking | 2026-06-24 | 3 | 2026-06-26 | Graph admin consent clears (P0); service mailbox; Teams policy | By Fri Day 5 (milestone) | Only AI contribution is optional outreach-text polish. Invite sent only after coordinator approval.
49 | P1 | Gate | GATE - Design freeze (end of Week 1). Later changes route to the defect or Phase-2 path | 2026-06-26 | 1 | 2026-06-26 | Module A demo on real Graph; Day-2 decisions | GATE - Day 5 (Fri 26-Jun) | Module A demonstrated end-to-end on real Graph by Friday; scope frozen.
PHASE 2 - Week 2 (Days 6-10, 29 Jun-3 Jul) - Functional Build (all six agents) [Development]
50 | P2 | Module B | Module B (Scorecard Input & Validation): native in-app form (1-5 across 4 categories / 16 parameters: Risk & Compliance, Performance, Commercial, Relationship) persisted in Postgres; Graph-mail requests + escalating reminders; deterministic validation (range, mandatory comment on 1/5, ~1.5-sigma outlier flag); compile internal-vs-vendor scorecard | 2026-06-29 | 4 | 2026-07-02 | Taxonomy locked (Day 2); Graph mail; Postgres | Days 6-10 | Replaces the Google Form + polling (supersedes the POC's 5-category interim set). LLM performs no part of scoring/validation. Scorecard request & reminder emails dispatched only after coordinator approval (approval gate).
51 | P2 | Module C | Module C (Internal Alignment): deterministic score deltas vs previous cycle; divergence flag where spread >= 1.5; LLM 'what changed' narrative + action-item extraction from notes; schedule internal-only Teams meeting via Graph | 2026-06-29 | 4 | 2026-07-02 | LLMProvider (Wk1); Graph; Postgres | Days 6-10 | LLM outputs reviewed/edited by coordinator; alignment invite sent only after approval.
52 | P2 | Module D | Module D (Vendor Prep): AI vendor brief (overall score/trend, per-category ratings, concerns, positives, open actions); 3 response stances (Factual / Neutral / Escalation) per pushback; deterministic guardrail suppresses AI drafting for legal-review items; unresolved-item tracking | 2026-06-29 | 4 | 2026-07-02 | LLMProvider (Wk1); Postgres | Days 6-10 | Internal-facing advisory material; no outbound comms of its own.
53 | P2 | Module E | Module E (EGB/QBR Meeting): pre-meeting facilitator briefing; live notes (5 types: Question/Objection/Decision/Appreciation/Action); pasted-transcript parse into structured notes; formal minutes; action-item extraction; distribute approved minutes via Graph mail | 2026-06-29 | 4 | 2026-07-02 | LLMProvider; Graph mail | Days 6-10 | Det-vs-AI split: LLM parses the transcript and drafts the facilitator briefing + formal minutes; the 5-type note classification, action-item register and workflow-state advance stay deterministic. Teams transcript ingestion out of scope - transcripts pasted in. Minutes held behind the approval gate.
54 | P2 | Module F | Module F (Cross-Cycle Memory & Trends): deterministic multi-cycle trends, recurring-issue detection (category below threshold for >= 2 consecutive cycles), trajectory classification (improving/stable/declining), LLM executive leadership brief, cross-vendor comparison | 2026-06-29 | 4 | 2026-07-02 | Postgres history; LLMProvider | Days 6-10 | Read-only/analytical; history now in Postgres rather than flat JSON. Only the leadership brief is LLM-generated; any leadership brief shared externally still follows the standard approval gate.
55 | P2 | Frontend | Shell-branded UI applied across the React 19 SPA (Design System + ApprovalPanel) | 2026-06-29 | 3 | 2026-07-01 | Brand/Comms assets (P0) | Days 6-8 | ApprovalPanel is the primary HITL surface for every AI draft.
56 | P2 | Frontend | Outlook-friendly HTML email templates (table-based layout, inline styles, plain-text fallback); cross-client render QA (Litmus / Email-on-Acid) | 2026-06-29 | 4 | 2026-07-02 | Brand sign-off by Day 8; Litmus acct (P0) | Day 8 (brand sign-off); QA by Day 10 | Verified render on Outlook desktop / OWA / mobile.
57 | P2 | Admin | Admin module: vendor master, user-role view, LLM budget panel, audit-log viewer, system-health view | 2026-06-29 | 4 | 2026-07-02 | Postgres; audit model | Days 6-10 | Operability surfaces for Shell IT Ops.
58 | P2 | Backend | Audit model: agent_runs, external_calls, security_events; append-only design mirrored to Log Analytics; correlation IDs propagated end-to-end; approver identity + timestamp recorded per outbound action (human accountability) | 2026-06-29 | 4 | 2026-07-02 | App Insights + Log Analytics (P0) | Days 6-10 | Append-only/auditability validated in Wk3. Each outbound communication is attributable to the named approving coordinator and timestamped. agent_runs holds vendor names + comments (Legal/Privacy sign-off).
59 | P2 | QA / Frontend | Automated accessibility checks (axe / Lighthouse) on the React 19 SPA | 2026-06-30 | 4 | 2026-07-03 | Branded UI (Day 8) | Days 7-10 (automated only) | Automated checks at launch; a formal manual WCAG audit is deferred to the warranty period / Phase 2 (Out of Scope at launch).
60 | P2 | Hardening | Hardening: rate limiting, token-budget guards + per-call caps, retry/backoff, correlation IDs | 2026-07-01 | 3 | 2026-07-03 | All six modules | Days 8-10 | Bounds LLM spend and protects against Graph throttling.
61 | P2 | QA | Add targeted automated test coverage (deterministic logic + smoke tests) - begins Wk2, continues Wk3 | 2026-06-30 | 3 | 2026-07-03 | Modules in build | Days 7-10 | POC has no test suite; focused coverage compensates under the compressed timeline.
62 | P2 | Milestone | Milestone - all six agents (A-F) functional end-to-end; functional build substantially complete | 2026-07-03 | 1 | 2026-07-03 | Modules A-F; UI; admin; audit | End of Wk2 (Fri 3-Jul) | Not the code freeze. Remaining completion + final hardening continue into early Wk3, up to the Day-13 code freeze.
PHASE 3 - Week 3 (Days 11-15, 6-10 Jul) - Completion, mid-week Code Freeze (Wed 8-Jul), Stabilisation & UAT [Development - no go-live]
63 | P3 | Completion | Final functional completion, integration polish & hardening (rate limiting, token-budget guards, retry/backoff, correlation IDs) - close out any remaining build | 2026-07-06 | 3 | 2026-07-08 | Functional build (Wk2) | Days 11-13 (by code freeze) | Any build work not finished in Wk2 is completed here, ahead of the mid-week code freeze.
64 | P3 | UAT | User Acceptance Testing with the 3 named VMO coordinators (all six modules A-F) | 2026-07-06 | 5 | 2026-07-10 | Modules functional; coordinators available (P0) | Days 11-15 | Risk-based manual UAT; begins on completed modules and intensifies after the Day-13 code freeze (defect fixes only thereafter). No production go-live this week.
65 | P3 | UAT | Defect triage across P1/P2/P3 with P1 resolved same-day; daily defect burn-down | 2026-07-06 | 5 | 2026-07-10 | UAT in progress | Days 11-15 | Daily stand-up reprioritisation; CAB contingency slot held for a late major defect.
66 | P3 | Ops | Complete observability, alerting and the operational runbook v1.0 | 2026-07-06 | 5 | 2026-07-10 | App Insights (P0) | Days 11-15 | Feeds the Wk3 observability gate and the Wk4 handover.
67 | P3 | Gate | GATE - Code freeze (middle of Week 3, Wed 8-Jul, Day 13). No further feature development; stabilisation & defect-fixes only | 2026-07-08 | 1 | 2026-07-08 | All six agents functional; final hardening complete | GATE - Day 13 (Wed 8-Jul) | From this point: defects only. Schema effectively frozen (additive-only migrations).
68 | P3 | QA | Regression + smoke testing of deterministic logic (slot ranking, score validation, workflow transitions) | 2026-07-08 | 3 | 2026-07-10 | Code freeze (Day 13) | Days 13-15 (post-freeze) | Validates the deterministic-first core behaves identically after re-platforming.
69 | P3 | QA / Security | Validate platform-layer capabilities: audit append-only behaviour, RBAC, app-only Graph auth, email rendering | 2026-07-08 | 3 | 2026-07-10 | Audit model; RBAC; Graph auth | Days 13-15 (post-freeze) | These platform traits are asserted-by-design in the POC and validated here before cutover.
70 | P3 | Gate | GATE - UAT sign-off (end of Week 3). All P1/P2 UAT defects closed; release candidate approved for deployment | 2026-07-10 | 1 | 2026-07-10 | UAT complete; defects closed | GATE - Day 15 (Fri 10-Jul) | Exit with a tested release candidate. P3 defects triaged into warranty/Phase 2.
PHASE 4 - Week 4 (Days 16-20, 13-17 Jul) - Security Sign-off, Deployment & Defect-Warranty
71 | P4 | Security | Shell IT Security review + sign-off on Graph permission scopes, Application Access Policy, RBAC, audit posture, and single-tenant isolation / data-residency (no Shell data outside Shell's boundary) | 2026-07-13 | 2 | 2026-07-14 | UAT sign-off; security artefacts | GATE - early Wk4 (Mon-Tue) | Engage Security liaison from Day 1 to avoid a late objection blocking cutover. Reviews deployment topology + data-flow for tenant isolation.
72 | P4 | Deployment Prereqs | Confirm production prerequisites landed: Conditional Access exemption for PROD service principal; production DNS hostname + public TLS certificate; Front Door/WAF prod config | 2026-07-13 | 2 | 2026-07-14 | CA path, DNS/TLS, Front Door (P0) | Before cutover (Wk4) | These were 'needed by Wk4' pre-mob items; confirm complete before the cutover window.
73 | P4 | Pilot Data | Vendor-master import (CSV/Excel) for the agreed single pilot vendor | 2026-07-13 | 2 | 2026-07-14 | Shell provides pilot vendor data (P0) | Before pilot kick-off (Wk4) | Late/incomplete vendor data delays the Wk4 pilot kick-off and handover even if the platform is live.
74 | P4 | Gate | GATE - CAB (Change Advisory Board) approval of the production change | 2026-07-14 | 1 | 2026-07-15 | Security sign-off | GATE - Wk4 (Wed) | Change Advisory Board approval is a precondition for cutover.
75 | P4 | Deployment | Production cutover / go-live: DNS change, deployment slot-swap, 60-minute observation window; tested rollback via slot-swap | 2026-07-15 | 1 | 2026-07-15 | CAB approval; DNS/TLS; Front Door | GATE - Wk4 (Wed-Thu) | System live in Shell's Azure subscription on App Service (Linux containers) behind Front Door + WAF.
76 | P4 | Pilot | Pilot vendor cycle kick-off in production, pair-shadowed by the Zensar Tech Lead | 2026-07-16 | 2 | 2026-07-17 | Cutover complete; vendor-master import | Wk4 (Thu-Fri) | One real pre-agreed pilot vendor cycle progressing with no open P1 issues.
77 | P4 | Handover | Coordinator training (recorded) + handover: runbook v1.0, documentation and the design decision log committed to Shell's repository | 2026-07-16 | 2 | 2026-07-17 | Cutover; runbook v1.0 (Wk3) | GATE - Wk4 (Thu-Fri) | Training delivered to the 3 named VMO coordinators; docs handed to Shell IT Ops.
78 | P4 | Warranty | Defect-warranty support begins (4-week period): Zensar fixes P1/P2 defects (P1 same-day where feasible) while Shell IT Ops runs BAU; P3 to backlog/Phase 2 | 2026-07-17 | 1 | 2026-07-17 | Go-live | Begins at go-live (Wk4) | Warranty start/end dates agreed in writing at handover. Post-freeze changes route to defect path or Phase 2.

## Pre-Mob Checklist
VendorPulse - EGB / QBR Process Automation
Pre-Mobilisation Dependency Checklist - what blocks Day 1 vs what is needed later
Phase 0 pre-mobilisation readiness window from Thu 18-Jun-2026 ¦ T-0 = Mon 22-Jun-2026 ¦ 4 working weeks (20 days): Wk1 22-26 Jun ¦ Wk2 29 Jun-3 Jul ¦ Wk3 6-10 Jul ¦ Wk4 13-17 Jul (deployment & warranty) ¦ CR-9 EGB
HARD Day-1 blockers must be complete by Monday of Week 1 (T-0 = 22-Jun). 'In progress / by <date>' items may still be open on Day 1 provided they land by the stated milestone.
# | Category | Dependency item | Owner | Lead time | Indicative cost | Blocks / required for | Day-1 status
Hard Day-1 blockers (complete by Mon of Week 1)
2 | Identity | Both Entra app registrations (NonProd + Prod) with certificate credentials | Shell Entra admin | 2-3 days | No incremental | App-only Graph auth; all email/calendar/Teams; SSO | HARD Day-1
3 | Identity | OIDC client + redirect URIs configured for SSO | Shell Entra admin | 1-2 days | No incremental | Any authenticated UI access | HARD Day-1
4 | Identity | Entra security groups for the four app roles | Shell Entra admin | 1-2 days | No incremental | RBAC; role-gated UI & approval routing | HARD Day-1
5 | M365 | Service mailbox provisioned + Exchange Application Access Policy applied | Shell Exchange admin | 2-5 days | ~$23-57/user/mo | From-identity for outbound mail; least-privilege scope | HARD Day-1
6 | Azure | Subscription + resource groups (nonprod + prod) with Zensar deploy access | Shell Azure admin | 2-5 days | Consumption | All deployment, IaC, CI/CD | HARD Day-1
7 | Azure | Azure Key Vault provisioned | Shell Azure admin | 1-2 days | Negligible | Secret storage; MI retrieval; cert object | HARD Day-1
8 | Azure | Azure Database for PostgreSQL Flexible Server provisioned | Shell Azure admin + DBA | 2-5 days | In prod estimate | Wk1 JSON->Postgres migration; all persistence | HARD Day-1
9 | Azure | App Service Plan (P1v3 prod / B2 nonprod) + Azure Container Registry | Shell Azure admin | 1-2 days | ~$220/mo prod | Application hosting; image build/push | HARD Day-1
10 | Azure | Private endpoints + VNet integration + Managed Identity role assignments | Shell Networking / Azure admin | 3-7 days | Modest | Secret-less runtime auth; DB & KV connectivity | HARD Day-1
11 | Azure | Outbound NAT / egress allow-listing to Graph + LLM endpoints | Shell Networking / IT Sec | 3-7 days | No incremental | All Graph & LLM calls from the VNet (hidden long pole) | HARD Day-1
12 | Azure | Azure Policy / tagging compliance | Shell Azure admin | 1-2 days | No incremental | Deployments pass governance | HARD Day-1
13 | LLM | LLM provider chosen + procurement initiated (contract/DPA in flight) | Shell Procurement + Legal | 4-8 wks (in flight) | ~$1,000/mo budget | All LLM text (C, D, E, F); key needed Wk2 | HARD Day-1 (decision)
14 | Tooling | Developer laptops (Python 3.11+, Node, Docker, Git) + admin rights | Zensar | Before Day 1 | Zensar-borne | All local development and build | HARD Day-1
15 | Tooling | Approved IDE (VS Code / JetBrains) + extensions | Zensar / Shell IT | Before Day 1 | Free / licence | Sanctioned toolchain | HARD Day-1
16 | Tooling | Claude Code / Claude for Work licences + Anthropic API dev key | Zensar / Anthropic | 1-2 wks if new | Per-seat + usage | AI-assisted pair-programming velocity | HARD Day-1
17 | Tooling | CI/CD repo created; Zensar engineers as guests; branch protection; CI/CD SP | Shell IT / DevOps | 3-7 days | Per licence | Day-1 branch & secret-scrub; all pipelines | HARD Day-1
18 | Connectivity | Network / VPN / device-compliance posture to reach tenant, repo, non-prod Graph | Shell IT Sec / Networking | 5-10 days | No incremental | Day-1 connectivity (hidden long pole) | HARD Day-1
19 | People | Product Owner / VMO lead + IT Architecture liaison named & available | Shell | Named pre-Day-1 | - | Daily decisions; Day-2 checkpoint; design-freeze sign-off | HARD Day-1
20 | Decisions | Pre-Day-1 decisions locked (LLM provider, region, mailbox name + from-identity/display name, DB+CMK, CI/CD, vendor-master format, external-attendee policy) | Shell + Zensar SA | Pre-Day-1 | - | Keeps the Day-2 checkpoint to design-level items only | HARD Day-1
May be in progress on Day 1, required by the date shown
22 | Identity | Graph application-permission admin consent (LONG POLE, 2-4 wk review) | Shell IT Sec + Entra | 2-4 wks | No incremental | Module A end-to-end on real Graph | By Day 5 (Fri 26-Jun)
23 | Identity | Conditional Access exemption / confirmed sign-in path for the SP | Shell IT Security | 2-5 days | No incremental | Service-principal Graph calls in PROD | PROD by Wk4
24 | Azure | Production DNS hostname + public TLS certificate | Shell Networking | 2-5 days | Cert cost | Wk4 DNS/TLS cutover | By Wk4
25 | Azure | Azure Front Door + WAF policy + App Insights/Log Analytics | Shell Azure / Networking | 2-4 days | In prod estimate | Public ingress; Wk4 cutover; Wk3 observability gate | Wk1 build / Wk4 cutover
26 | Pilot | Vendor-master import (CSV/Excel) for the pilot vendor | Shell PO | - | - | Wk4 pilot vendor cycle kick-off | By Wk4 kick-off
27 | Brand | Brand / Comms sign-off on Shell-branded email templates | Shell Brand/Comms | - | - | Templates built & rendered in Wk2 | By Day 8 (Wk2)
28 | M365 | Litmus / Email-on-Acid account for cross-client render QA | Shell or Zensar | 1-3 days | ~$99/mo | Outlook render acceptance (Day 8 templates) | By Day 8
29 | People | 3 named VMO coordinators for UAT | Shell | Named pre-Day-1 | - | Wk3 UAT; Wk4 training & handover | Active Wk3-4

## Quality Gates
VendorPulse - EGB / QBR Process Automation
Quality Gates - five sequential gates; each must pass before the next stage proceeds
Phase 0 pre-mobilisation readiness window from Thu 18-Jun-2026 ¦ T-0 = Mon 22-Jun-2026 ¦ 4 working weeks (20 days): Wk1 22-26 Jun ¦ Wk2 29 Jun-3 Jul ¦ Wk3 6-10 Jul ¦ Wk4 13-17 Jul (deployment & warranty) ¦ CR-9 EGB
# | Gate | Timing | Pass condition
1 | Day-2 Design Alignment Checkpoint | Week 1, Day 2 (Tue 23-Jun) | ~12 design decisions locked (scorecard mechanism, 4-cat/16-param taxonomy, brief/minutes output formats, vendor-master source, approval routing).
2 | Design freeze | End of Week 1 (Fri 26-Jun, Day 5) | Scope frozen; Module A demonstrated end-to-end on real Graph by Friday. Later changes route to the defect or Phase-2 path.
3 | Code freeze | Middle of Week 3 (Wed 8-Jul, Day 13) | All six agents functional; scorecard collection in chosen mode; Shell-branded UI; Outlook templates; admin module; final hardening complete. From here: defects only - stabilisation & UAT.
4 | UAT sign-off | End of Week 3 (Fri 10-Jul, Day 15) | UAT complete with all P1/P2 defects closed; release candidate approved for deployment. No production go-live this week.
5 | Security sign-off | Week 4 (Mon-Tue 13-14 Jul) | Shell IT Security review passed on Graph scopes, Application Access Policy, RBAC, audit posture; observability, alerts and runbook in place.
6 | CAB approval & production cutover | Week 4 (Wed-Thu 15-16 Jul) | Change Advisory Board approval; production cutover (DNS, slot-swap, 60-min observation); pilot vendor cycle kicked off.
7 | Handover | Week 4 (Thu-Fri 16-17 Jul) | Coordinator training delivered & recorded; runbook v1.0, documentation and decision log handed over; defect-warranty begins.

## Risk Register
VendorPulse - EGB / QBR Process Automation
Consolidated Risk Register - residual risk concentrated in the pre-mobilisation window
Phase 0 pre-mobilisation readiness window from Thu 18-Jun-2026 ¦ T-0 = Mon 22-Jun-2026 ¦ 4 working weeks (20 days): Wk1 22-26 Jun ¦ Wk2 29 Jun-3 Jul ¦ Wk3 6-10 Jul ¦ Wk4 13-17 Jul (deployment & warranty) ¦ CR-9 EGB
# | Category | Risk | Likelihood | Impact | Mitigation | Owner
1 | Tooling/velocity | Developer laptops not provided with full local env + admin rights | Low | High | Confirm laptop/device readiness as a Zensar-controlled pre-mob go/no-go gate; Zensar-managed devices as fallback under Shell device-compliance | Zensar Delivery Mgr / Shell IT
2 | Tooling/velocity | VS Code / approved IDE + extensions not approved | Low | Medium | Lock IDE choice and extension list with Shell IT before Day 1; go/no-go gate | Shell IT / Zensar Delivery Mgr
3 | Tooling/velocity | Claude Code / Anthropic developer licences not procured | Low | High | Procure Claude for Work licences + API dev key in pre-mob; go/no-go gate | Zensar Delivery Mgr / Procurement
4 | Tooling/velocity | Network / VPN / device compliance prevents reaching Shell tenant, repo, non-prod Graph | Medium | High | Agree access posture and VPN/BYOD path in pre-mobilisation | Shell Networking / Security
5 | Tooling/velocity | Source-control + CI/CD guest onboarding slow (guests, branch protection, CI/CD SP) | Medium | High | Provision repo guest access, branch protection and CI/CD SP pre-Day-1; treat as Day-1 blocker (3-7 day onboarding) | Shell IT / Zensar DevOps
6 | Identity/Graph | Graph app-only admin consent not granted in time | High | High | Start admin consent ~4-6 wks ahead (2-4 wk review, LONG POLE); track daily; mock only for internal demo | Shell Entra admin / IT Security
7 | Identity/Graph | Application Access Policy not offered/accepted, so tenant-wide consent is refused | Medium | High | Propose mailbox-scoped Application Access Policy up front; couple policy + consent as one security-review package | Shell IT Security / Exchange admin
8 | Identity/Graph | Service mailbox / Application Access Policy not provisioned or mis-scoped | Medium | High | Provision vendorpulse-svc mailbox + E3/E5 licence and apply the scoping policy in pre-mob; offer policy up front | Shell Exchange admin
9 | Identity/Graph | Graph certificate not generated/uploaded in time, or client-secret used against preference | Medium | High | Agree cert ownership (Shell-generated preferred) + thumbprint handover; store as Key Vault cert object; 12-month auto-renewal | Shell Entra admin / Zensar DevOps
10 | Identity/Graph | Microsoft Graph API throttling (429 / 5xx) | Medium | Medium | Retry/backoff engineered in GraphService; correlation IDs; batch requests where possible | Zensar Tech Lead
11 | Identity/Graph | Conditional Access blocks the service principal | Medium | High | CA exemption or confirmed sign-in path agreed with Entra admin pre-Day-1 | Shell Entra admin
12 | Identity/Graph | External / guest meeting policy blocks vendor invites | Medium | High | Confirm external-attendee policy for the service mailbox in pre-mobilisation | Shell Exchange/Teams admin
13 | Azure/Network | Outbound egress / NAT allow-listing to Graph + LLM endpoints not configured | Medium | High | Agree the egress allow-list (Graph + Anthropic/Azure OpenAI) with Shell Networking pre-mob; validate from non-prod in Wk1 | Shell Networking / Zensar DevOps
14 | Azure/Network | Private endpoints / VNet integration to Postgres & Key Vault not in place | Medium | High | Provision private endpoints + VNet integration + MI role assignments pre-mob; smoke-test secret retrieval & DB connectivity Day 1 | Shell Networking / Azure admin / Zensar DevOps
15 | Azure/Network | No SQL schema yet + messy POC SQLite/JSON data (13 entities -> ~15 tables) | Medium | Medium | Alembic schema + asyncpg planned Day 1; data cleansing scoped; defaults for missing fields; additive-only migrations after Day-13 freeze | Zensar Backend / Tech Lead
16 | Azure/Network | Azure estate incomplete (RGs, Postgres, KV, App Service, Front Door/WAF, App Insights, role assignments, egress) | Medium | High | Complete Azure provisioning in pre-mob; validate MI role assignments Day 1 | Shell Azure admin / Zensar DevOps
17 | Azure/Network | DNS / TLS cutover failure in Week 4 | Low | High | Provision DNS+TLS in pre-mob; slot-swap with rollback; 60-min observation window | Shell Networking / Zensar DevOps
18 | LLM/Compliance | LLM enterprise contract / DPA / EU-residency not signed | Medium | High | Start contract 4-8 wks ahead; LLMProvider abstraction enables config-only switch to Azure OpenAI | Shell Procurement / Legal/Privacy
19 | LLM/Compliance | Azure OpenAI quota / region approval not granted (if chosen) | Low-Medium | Medium | Submit Microsoft quota request in chosen region 2-4 wks ahead; confirm tool-calling-capable gpt-4o-class in West Europe | Shell Azure admin / Zensar Tech Lead
20 | LLM/Compliance | Azure OpenAI deployment misconfigured (preview / non-chat model) | Low | Medium | Specify a gpt-4o-class chat deployment explicitly; validate connectivity in Wk1 | Shell Azure admin / Zensar Tech Lead
21 | LLM/Compliance | LLM token-spend overrun | Medium | Medium | Token-budget guards + per-call caps; admin LLM budget panel; monthly budget agreed | Zensar Tech Lead / Shell PO
22 | LLM/Compliance | LLM provider outage mid-cycle blocks the workflow | Low | Medium | Graceful degradation: deterministic workflow proceeds with the LLM disabled; AI text optional/never blocking; LLM feature flag; coordinators proceed manually | Zensar Tech Lead
23 | LLM/Compliance | PII / data-residency / audit-retention sign-off late (agent_runs holds vendor names + comments) | Medium | High | Engage Legal/Privacy pre-Day-1; EU residency in DPA; retention policy + immutable audit trail agreed | Shell Legal/Privacy / IT Security
24 | Scope/Schedule | Scorecard taxonomy not locked | Medium | High | Lock 4-category / 16-parameter taxonomy at the Day-2 design checkpoint | Shell Product Owner / VMO lead
25 | Scope/Schedule | Scorecard form-platform decision late | Medium | High | Native in-app form recommended and pre-agreed; confirmed at Day-2 checkpoint | Shell PO / Zensar SA
26 | Scope/Schedule | Day-2 checkpoint produces too many in-scope changes (buffer exhausted) | Medium | High | Strict change-control; route non-essentials to Phase 2 / warranty; formal re-baseline if breached | Zensar Delivery Mgr / Shell PO
27 | Scope/Schedule | Post-freeze (mid-Wk3, Day-13) scope changes | Medium | High | Design frozen end of Wk1, code frozen mid-Wk3 (Day 13); later changes follow defect or Phase-2 path; change-control board | Zensar Delivery Mgr / Shell PO
28 | Scope/Schedule | One major UAT defect pushes cutover past its Wk4 slot | Medium | High | P1 same-day triage; daily defect burn-down; CAB contingency slot held | Zensar QA / Delivery Mgr
29 | Scope/Schedule | Outlook email-rendering issues found late | Medium | Medium | Table-based inline-style HTML + plain-text fallback; Litmus / Email-on-Acid QA in Wk2 | Zensar Frontend / QA
30 | Scope/Schedule | Zensar team-member unplanned absence (no-PTO assumption) | Medium | High | Cross-skilling; Tech Lead / Solution Architect cover; daily stand-up reprioritisation | Zensar Delivery Mgr
31 | Scope/Schedule | Late IT-Security objection blocking cutover | Medium | High | Engage Security liaison from Day 1; design review early; Wk4 security sign-off planned | Shell IT Security / Zensar SA
32 | Scope/Schedule | No automated tests exist today (quality risk under compressed timeline) | High | Medium | Risk-based manual UAT with 3 named coordinators; focus on deterministic logic; smoke tests; defects triaged in warranty | Zensar QA

## Acceptance Criteria
VendorPulse - EGB / QBR Process Automation
Acceptance Criteria - Definition of Done for the pilot go-live (evidenced in Shell's tenant)
Phase 0 pre-mobilisation readiness window from Thu 18-Jun-2026 ¦ T-0 = Mon 22-Jun-2026 ¦ 4 working weeks (20 days): Wk1 22-26 Jun ¦ Wk2 29 Jun-3 Jul ¦ Wk3 6-10 Jul ¦ Wk4 13-17 Jul (deployment & warranty) ¦ CR-9 EGB
Verified jointly by the Zensar Tech Lead & Solution Architect with Shell's Product Owner (VMO lead) and IT Security liaison during Week-3 UAT and at the Week-4 production cutover. Evidence (demo / screenshot / log entry / sign-off) is captured per item and retained in the decision log committed to Shell's repository.
# | Area | Criterion | Evidence of acceptance
Platform & Security
1 | Platform & Security | Production environment live | Running in Shell's Azure subscription on App Service (Linux containers) behind Front Door + WAF; nonprod & prod RGs in place.
2 | Platform & Security | Entra ID SSO | A Shell user signs in via Entra ID (Azure AD) OIDC SSO; no local credentials exist.
3 | Platform & Security | RBAC enforced | Four roles (VMO coordinator, VMO admin, executive sponsor, viewer) mapped to Entra security groups; correctly gate UI & API access.
4 | Platform & Security | Secrets management | No secrets in code or .env; all secrets resolved from Key Vault via Managed Identity. POC secrets scrubbed from history and rotated.
5 | Platform & Security | Database | Data persisted in Azure PostgreSQL Flexible Server (HA / zone-redundant in prod); JSON-file persistence retired.
6 | Platform & Security | Observability & audit | App Insights + Log Analytics active; correlation IDs flow end-to-end; immutable audit trail records all actions & approvals; each outbound communication is attributable to the named approving coordinator and timestamped.
7 | Platform & Security | Single-tenant isolation & scope boundary | Deployed solely within Shell's Azure subscription + M365 tenant; no Shell data stored outside Shell's boundary. Launch is English-only, web-only (desktop browser); multi-language UI, mobile/native clients and multi-tenancy are out of scope. Evidenced by deployment-topology + data-flow review at the Wk4 security sign-off.
8 | Platform & Security | Graceful degradation | If the LLM provider is unavailable, the deterministic workflow continues; AI-assisted text is optional and never blocking; coordinators can proceed manually. LLM features are disable-by-configuration.
9 | Platform & Security | Security sign-off | Shell IT Security review completed and signed off in Week 4.
Functional (A-F)
10 | Functional (A-F) | A - Scheduling & Coordination | Roster refreshed; attendance outreach sent; candidate times via Graph findMeetingTimes against real mailboxes; slots ranked deterministically (organiser + sponsor free = hard constraint; soft scoring on attendance %, calendar conflicts, timezone fit); Teams meeting + invite via Graph after approval; RSVPs tracked.
11 | Functional (A-F) | B - Scorecard Input & Validation | Personalised requests via Graph mail (approved before dispatch); responses via native in-app form (1-5 across 4 categories - Risk & Compliance, Performance, Commercial, Relationship - / 16 parameters); escalating reminders; deterministic validation (range, mandatory comment on 1/5, ~1.5-sigma outlier); internal-vs-vendor scorecard compiled.
12 | Functional (A-F) | C - Internal Alignment | Score deltas vs previous cycle; divergence flagged where spread >= 1.5; LLM 'what changed' narrative + action-item extraction; internal-only Teams alignment meeting scheduled via Graph after approval.
13 | Functional (A-F) | D - Vendor Prep | AI vendor brief (score/trend, per-category, concerns, positives, open actions); 3 response stances (Factual/Neutral/Escalation) per pushback; AI drafting suppressed for legal-review items; unresolved items tracked.
14 | Functional (A-F) | E - EGB/QBR Meeting | Pre-meeting facilitator briefing; live notes across the 5 types; pasted transcript parsed into structured notes; formal minutes; action items extracted; approved minutes distributed via Graph mail. AI parses transcript + drafts briefing/minutes; 5-type classification, action-item register and state advance are deterministic.
15 | Functional (A-F) | F - Cross-Cycle Memory & Trends | Multi-cycle trends; recurring-issue detection (category below threshold for >= 2 cycles); per-vendor trajectory; executive leadership brief; cross-vendor comparison. Read-only; any externally-shared brief follows the approval gate.
16 | Functional (A-F) | Workflow & gate invariants | 12-state forward-only machine behaves correctly (CYCLE_CREATED -> ATTENDEE_REFRESH_SENT -> AVAILABILITY_COLLECTED -> MEETING_SCHEDULED -> SCORECARD_REQUEST_SENT -> SCORECARD_COLLECTION -> SCORECARD_COMPILED -> INTERNAL_ALIGNMENT -> VENDOR_PREP -> MEETING_IN_PROGRESS -> POST_MEETING_COMPLETE -> ARCHIVED; invalid transitions rejected); human-approval gate enforced on every outbound action; deterministic-first / AI-second preserved (LLM only produces human-readable text).
Integration (Graph / Teams / Outlook)
17 | Integration (Graph / Teams / Outlook) | App-only certificate auth | All email/calendar/Teams operations via Graph using app-only auth with a certificate (MSAL client-credentials); no user/delegated bearer token.
18 | Integration (Graph / Teams / Outlook) | Service-mailbox sender | Outbound mail sent from the dedicated service mailbox, constrained by the Exchange Application Access Policy.
19 | Integration (Graph / Teams / Outlook) | Google stack removed | Google / Gmail / Google Forms removed entirely from codebase and runtime.
20 | Integration (Graph / Teams / Outlook) | Teams meetings | Teams online meetings created via Graph for vendor-facing and internal-only meetings; vendor (external) attendees invitable per confirmed policy.
21 | Integration (Graph / Teams / Outlook) | Outlook email rendering | Table-based inline-style HTML renders acceptably on Outlook desktop, OWA & mobile, with plain-text fallback; verified via cross-client render QA.
22 | Integration (Graph / Teams / Outlook) | Graph resilience | Graph calls resilient under load (retry/backoff on 429 & 5xx).
Operations & Handover
23 | Operations & Handover | Admin module | Vendor master, user-role view, LLM budget panel, audit-log viewer, system-health view all complete.
24 | Operations & Handover | Branding | Shell branding applied across the UI.
25 | Operations & Handover | Observability & runbook | Dashboards, alerts and runbook v1.0 in place; runbook handed to Shell IT Ops.
26 | Operations & Handover | Training | Coordinator training delivered to the 3 named VMO coordinators and recorded.
27 | Operations & Handover | Documentation | Architecture docs, decision log and supporting docs committed to Shell's repository.
28 | Operations & Handover | LLM budget | LLM operating within the agreed monthly token budget, with budget guards and rate limiting active.
29 | Operations & Handover | Accessibility | Automated accessibility checks (axe / Lighthouse) pass on the SPA at launch; a formal manual WCAG audit is deferred to warranty / Phase 2.
Pilot
30 | Pilot | Live pilot cycle | One real, pre-agreed pilot vendor cycle progressing through the workflow in production with no open P1 issues.
31 | Pilot | UAT complete | UAT completed with the 3 named VMO coordinators.
32 | Pilot | Defects closed | All P1 & P2 UAT defects closed; P3 triaged and scheduled (warranty or Phase 2).
33 | Pilot | Cutover | Production cutover completed in Wk4 (DNS, slot-swap, 60-min observation) with CAB approval.
Delivery Gates (all must pass in sequence)
34 | Delivery Gates (all must pass in sequence) | Design alignment / freeze | Day-2 checkpoint locks ~12 decisions; design frozen end of Wk1; Module A demonstrated end-to-end on real Graph by Friday of Wk1.
35 | Delivery Gates (all must pass in sequence) | Code freeze | Mid Wk3 (Wed 8-Jul, Day 13): all six agents functional; scorecard collection in chosen mode; Shell-branded UI; Outlook templates; admin module; final hardening complete. From here: defects only.
36 | Delivery Gates (all must pass in sequence) | UAT sign-off | End of Wk3 (Day 15): UAT complete with all P1/P2 defects closed; release candidate approved. No production go-live this week.
37 | Delivery Gates (all must pass in sequence) | Security sign-off | Wk4: Shell IT Security review passed; observability, alerts and runbook in place.
38 | Delivery Gates (all must pass in sequence) | CAB approval & cutover | Wk4: CAB approval; production cutover (DNS, slot-swap, 60-min observation); pilot vendor cycle kicked off.
39 | Delivery Gates (all must pass in sequence) | Handover | Wk4: coordinator training delivered & recorded; runbook v1.0, documentation and decision log handed over.
Warranty Terms
40 | Warranty Terms | 4-week defect warranty | After go-live, Zensar fixes P1/P2 defects (P1 same-day where feasible) while Shell IT Ops runs BAU; P3 scheduled into warranty backlog or Phase 2 by agreement.
41 | Warranty Terms | Post-freeze change routing | Any design/functional change requested after the Wk1 design freeze routes to the defect path or a Phase-2 change; not part of pilot acceptance.
42 | Warranty Terms | Warranty dates | Warranty start and end dates are agreed in writing as part of go-live sign-off.