VendorPulse — Dependencies & Access Requirements

Shell engagement · Version 2.0 · 2026-06-03

Dependencies & Access Requirements

Version: 2.0 | Date: 2026-06-03 Audience: Shell IT Service Management, Shell Identity, Shell Procurement, Zensar Delivery Manager Purpose: Single checklist of everything the delivery team needs in order to build, deploy, and operate VendorPulse for Shell

How to read this document

Every row is something that must exist before the dependent piece of work can start. Items are grouped by domain (Identity, Azure, LLM, Messaging, Tooling, People). Each item has:

• Owner — who provides / approves it (usually Shell)

• Lead time — how long it typically takes to obtain

• Blocks — what cannot start until this is in place

• Cost note — explicit licence / subscription cost where applicable

We have deliberately erred on the side of "request it earlier than you think you need it". Several items below have multi-week lead times that, if missed, push the entire timeline.

1. Microsoft Entra ID (Identity)

| # | Item | Owner | Lead time | Blocks |
| --- | --- | --- | --- | --- |
| I1 | Two app registrations in Shell Entra ID: VendorPulse-NonProd and VendorPulse-Prod | Shell Entra ID admin | 1 week | All Graph + OIDC integration |
| I2 | Certificate-based credential for each app registration. Cert generated by Shell (preferred) or by Zensar and uploaded; thumbprint shared back | Shell Entra ID admin + Zensar | 1 week | App-only Graph auth |
| I3 | Admin consent on Graph application permissions: Mail.Send, Calendars.ReadWrite, OnlineMeetings.ReadWrite.All, User.Read.All, MailboxSettings.Read, Group.Read.All | Shell Entra ID admin (global admin role required) | 2–4 weeks (security review) | Module A and Module B |
| I4 | OIDC client (delegated) for the SPA's user authentication. Same app registration, with User.Read delegated permission | Shell Entra ID admin | with I1 | All authenticated app access |
| I5 | Entra ID security groups for app roles: shell-vmo-admins, shell-vmo-coordinators, shell-vmo-sponsors, shell-vmo-viewers. Each group populated by Shell with the appropriate personnel | Shell IAM team | 1–2 weeks | App-level RBAC |
| I6 | Application Access Policy scoping Mail.Send and Calendars.ReadWrite to the service mailbox only | Shell Exchange admin | 1 week | Mailbox-constrained sending — required for security review approval |
| I7 | Conditional Access policy exemption for the app's service principal (or a confirmed sign-in path that does not block app-only auth) | Shell Identity team | 1–2 weeks | All Graph calls in production |
| I8 | Two redirect URIs configured on the OIDC app: https://vendorpulse-nonprod.<shell>.com/api/v1/auth/callback and the prod equivalent | Shell Entra ID admin | with I1 | User SSO flow |

2. Microsoft 365 — Messaging & Calendar

| # | Item | Owner | Lead time | Blocks | Cost note |
| --- | --- | --- | --- | --- | --- |
| M1 | Service mailbox `vendorpulse-svc@shell.com` (or naming per Shell standards) with Microsoft 365 E3 or E5 license | Shell Messaging team | 1 week | All Graph mail + calendar usage | ~$23/user/month for E3, ~$57/user/month for E5 |
| M2 | Mailbox storage allocated to ~10 GB to accommodate cycle history + replies | Shell Messaging team | with M1 | Long-term operation |  |
| M3 | Mailbox retention policy — auto-archive after 1 year for sent items | Shell Records / Messaging | 2 weeks | Compliance |  |
| M4 | Distribution lists or shared mailboxes for VMO Coordinator notifications (optional — for routing replies into Teams channel) | Shell Messaging team | 1 week | Reply visibility |  |
| M5 | Teams meeting policy allowing the service mailbox to create online meetings via Graph | Shell Teams admin | 1 week | Module A invite creation |  |
| M6 | External sharing / guest meeting policy confirmation — can the service mailbox invite vendors as external attendees? | Shell IT Security | 2 weeks | Inviting external vendor attendees |  |
| M7 | Litmus / Email on Acid subscription for cross-client email rendering testing during Week 2 | Zensar (or Shell, if preferred) | Immediate | Email template QA | ~$99/month |

3. Azure Subscription & Infrastructure

| # | Item | Owner | Lead time | Blocks | Cost note (estimate) |
| --- | --- | --- | --- | --- | --- |
| A1 | Azure subscription (existing Shell IT subscription or new) with permission for Zensar engineers to deploy via service principal | Shell Cloud team | 2 weeks | All deployment | n/a |
| A2 | Resource groups: rg-vendorpulse-nonprod-weu, rg-vendorpulse-prod-weu | Shell Cloud team | with A1 | Resource provisioning | n/a |
| A3 | Azure App Service Plan — P1v3 (1 vCPU, 8 GB RAM) for prod, B2 for non-prod. Production HA via 2 instances. | Shell Cloud team | with A1 | Backend + frontend hosting | ~$220/month prod, ~$33/month non-prod |
| A4 | Azure Database for PostgreSQL Flexible Server — Burstable B2ms (2 vCPU, 4 GB RAM) for prod, B1ms for non-prod, with HA mode (zone-redundant) for prod | Shell DBA team | 1 week | Data persistence | ~$130/month prod, ~$15/month non-prod (HA adds ~50%) |
| A5 | Azure Key Vault (Standard tier) per environment | Shell Cloud team | 1 week | Secret storage | ~$5/month |
| A6 | Azure Front Door (Standard) with WAF policy | Shell Cloud team | 2 weeks | Public-facing entry, WAF | ~$35/month + traffic |
| A7 | Application Insights workspace linked to a Log Analytics workspace | Shell Observability team | 1 week | Telemetry + audit | Pay-as-ingested; ~$50–$150/month at expected volume |
| A8 | Azure DNS zone or CNAME in *.shell.com for vendorpulse.it.shell.com and vendorpulse-nonprod.it.shell.com | Shell DNS / Networking | 1–2 weeks | Public access | n/a |
| A9 | TLS certificate (wildcard or specific) for the public hostname | Shell PKI team | 1–2 weeks | HTTPS | n/a |
| A10 | Private endpoint subnets and VNet integration for App Service ↔ Postgres ↔ Key Vault | Shell Networking team | 1–2 weeks | Network isolation | ~$10/month per private endpoint |
| A11 | Managed Identity on App Service with role assignments: Key Vault Secrets User, Postgres pg_monitor + per-DB grants, Log Analytics contributor | Shell IAM / Cloud | 1 week | Production secret access without .env |  |
| A12 | Outbound NAT IP allowlisting to Microsoft Graph and Anthropic / Azure OpenAI endpoints if Shell mandates egress control | Shell Networking | 2 weeks | All external integration calls |  |
| A13 | Azure Policy compliance review — ensure deployed resources satisfy Shell's standard Azure Policies (tagging, encryption, allowed locations) | Shell Cloud Governance | 2 weeks | Production go-live |  |

Estimated Azure run cost: ~$450–$650/month for prod environment at expected load (5–25 concurrent users, ~10,000 LLM calls/month). Non-prod adds ~$80–$120/month. Final figures depend on actual Postgres tier and observability ingestion volume.

4. LLM Provider — Choose Anthropic OR Azure OpenAI

4.1 Option A — Anthropic API (recommended)

| # | Item | Owner | Lead time | Cost note |
| --- | --- | --- | --- | --- |
| L1a | Anthropic enterprise account in Shell's name (or routed through Zensar's account with explicit Shell-tenancy contract) | Shell Procurement + Anthropic | 4–8 weeks | Variable; enterprise pricing typically $50–$200 per million input tokens, varies by model |
| L2a | Anthropic enterprise DPA specifying zero-data-retention, no-training, EU data residency | Shell Legal | 4–6 weeks (parallel with L1a) | Included in enterprise contract |
| L3a | API key issued, stored in Key Vault | Anthropic + Shell IT | 1 day after L1a | n/a |
| L4a | Monthly LLM budget agreed (we recommend ~$1,000/month for the workload, padded for surprises) | Shell finance | with L1a | $12,000/year nominal |

4.2 Option B — Azure OpenAI (alternative)

| # | Item | Owner | Lead time | Cost note |
| --- | --- | --- | --- | --- |
| L1b | Azure OpenAI service quota approval in Shell's Azure subscription (Microsoft application form, region-specific) | Shell + Microsoft | 2–4 weeks | n/a |
| L2b | Model deployment(s) for gpt-4-turbo or gpt-4o (whichever is current and tool-calling-capable) in West Europe | Shell Cloud + Microsoft | 1–2 weeks after L1b | Pay-per-token; rough parity with Anthropic |
| L3b | Existing Microsoft enterprise terms cover data handling — verify scope of "no training" clause with Microsoft account team | Shell Legal | 1 week | Included in EA |
| L4b | API key + endpoint URL stored in Key Vault | Shell Cloud + Microsoft | 1 day after L2b | n/a |

Decision required from Shell during pre-mobilisation (before Day 1). Our recommendation is Option A — Anthropic because:

The POC has been built and tuned against Claude's tool-calling semantics; switching costs are non-zero

Anthropic's tool-calling reliability for the agent pattern is, in our experience, currently best in class

Enterprise terms are negotiable and equivalent to Azure OpenAI on the data-protection axis

Option B remains viable; switching either direction is a configuration change, not a code change (see §05 LLD §8).

5. Developer & Operational Tooling

| # | Item | Owner | Lead time | Cost note |
| --- | --- | --- | --- | --- |
| T1 | Azure DevOps or GitHub Enterprise organisation/project for Shell with Zensar engineers as guests | Shell Engineering Productivity | 1–2 weeks | Included in Microsoft EA |
| T2 | Source code repo initialised with branch protection (no direct push to main) | Shell + Zensar | 1 day after T1 | n/a |
| T3 | CI/CD service connection — service principal for the pipeline to deploy to App Service, Postgres, Key Vault | Shell IAM | 1 week | n/a |
| T4 | Artifact registry — Azure Container Registry (Standard tier) or GitHub Packages | Shell Cloud | 1 week | ~$5/month |
| T5 | Static analysis tooling — SonarQube / SonarCloud or equivalent (if Shell standard) | Shell Engineering | 1 week | per Shell licence |
| T6 | Secrets scanning in CI — TruffleHog, GitLeaks, or Azure DevOps secret-scanning | Shell + Zensar | 1 week | Free |
| T7 | Container vulnerability scanning — Trivy or Snyk in CI | Shell + Zensar | 1 week | Snyk paid; Trivy free |
| T8 | Dependabot / Renovate enabled on the repo | Zensar | 1 day | Free |
| T9 | Anthropic SDK access — Claude API key with developer-tier usage for non-prod runs during build | Zensar | 1 day | Pay-per-token; ~$200–$500/month for non-prod dev usage |
| T10 | Claude Code / IDE assistant subscription (Claude Pro or Claude for Work) for the engineering team — speeds up implementation significantly | Zensar (covered) | 1 day | $20/user/month (Pro) or per Claude for Work pricing |
| T11 | Litmus or Email on Acid for email template QA — already mentioned in §2.M7 | Zensar | 1 day | ~$99/month |
| T12 | Playwright cloud / BrowserStack for cross-browser E2E (optional — local works) | Zensar | 1 week | $39/user/month (BrowserStack) |

6. Shell People & Roles

| # | Role (Shell-side) | What we need | Time commitment | Lead time |
| --- | --- | --- | --- | --- |
| P1 | Executive Sponsor (Shell VP-level) | Aware of scope; available for weekly steering check-in and escalation | ~2h/week | from kick-off |
| P2 | Product Owner (Shell VMO lead) | Owns the requirements, scorecard taxonomy, vendor master, UAT sign-off; co-chairs Day-2 design alignment checkpoint | Daily for the 3 weeks | from Day 1 |
| P3 | IT Architecture Liaison | Reviews architecture, signs off ADRs at pre-mobilisation; attends Day-2 design alignment checkpoint | ~5h Day 1–5, ad-hoc thereafter | pre-mobilisation |
| P4 | IT Security Liaison | Pre-mobilisation security review + Day-13 pre-prod sign-off | ~5h pre-mobilisation, ~3h Days 11–13 | pre-mobilisation |
| P5 | Entra ID Admin | Creates app registrations, grants admin consent, manages groups — all complete before Day 1 | as needed | pre-mobilisation |
| P6 | Exchange / Messaging Admin | Provisions service mailbox, applies Application Access Policy, sets retention — complete before Day 1 | as needed | pre-mobilisation |
| P7 | Azure Cloud Admin | Provisions subscriptions, resource groups, manages role assignments — complete before Day 1 | as needed | pre-mobilisation |
| P8 | DBA | Provisions Postgres before Day 1; signs off schema migrations during Week 1 | as needed | pre-mobilisation |
| P9 | Networking | Configures VNet integration, private endpoints, egress, DNS — complete before Day 1 | as needed | pre-mobilisation |
| P10 | Procurement | Onboards LLM provider contract — complete before Day 1 | as needed | pre-mobilisation |
| P11 | Legal / Privacy | DPAs, data residency confirmation — complete before Day 1 | as needed | pre-mobilisation |
| P12 | VMO Coordinators (3 named individuals) | Pilot users; provide UAT feedback Week 3 | ~10h across Days 11–15 | Week 3 |
| P13 | Brand / Communications | Confirms colour palette, logo, email tone — attends Day-2 design alignment | ~3h, one-off | Day 1 / Day 2 |

7. Zensar Team

For reference — the team Zensar will assign:

| Role | Allocation | Duration |
| --- | --- | --- |
| Delivery Manager | 100% | All 3 weeks |
| Solution Architect | 100% | All 3 weeks (heavier in Week 1, design checkpoint co-chair) |
| Tech Lead | 100% | All 3 weeks |
| Backend Engineer × 2 | 100% | All 3 weeks |
| Frontend Engineer × 2 | 100% | All 3 weeks |
| QA Engineer | 100% | All 3 weeks (heaviest in Week 3 — UAT support and defect verification) |
| DevOps / Cloud Engineer | 100% | All 3 weeks (heavier in Weeks 1 and 3 — bring-up and cutover) |

The compressed plan assumes no PTO during the 3 weeks across all roles. Any PTO must be pre-declared and re-baselined into the plan.

8. Pre-existing Knowledge Required

For Shell-side decisions before Day 1 of delivery (confirmed during pre-mobilisation; remaining items locked at the Day-2 design alignment checkpoint):

| Decision needed | Owner | Default we will propose |
| --- | --- | --- |
| LLM provider (Anthropic vs Azure OpenAI) | Shell IT Security + Procurement | Anthropic |
| Hosting region | Shell Cloud | West Europe |
| Service mailbox name | Shell Messaging | vendorpulse-svc@shell.com |
| Database (Postgres vs SQL Server) | Shell DBA | Postgres |
| CI/CD platform (Azure DevOps vs GitHub Enterprise) | Shell Engineering | Azure DevOps |
| Scorecard taxonomy locked | Shell VMO | The taxonomy embedded in the POC (Risk/Performance/Commercial/Relationship), validated by VMO |
| Vendor master format | Shell VMO | Excel/CSV import for pilot; future integration with SAP/Ariba |
| Customer-managed keys (CMK) on day one? | Shell IT Security | Yes — defaults to Azure-managed, easy to enable CMK if asked |
| Email "from" identity for vendor-facing emails | Shell Brand + VMO | vendorpulse-svc@shell.com with "VendorPulse — Shell VMO" display name |
| External attendees in Teams meetings | Shell IT Security | Allowed per current policy; confirm |

9. Checklist summary — what blocks Day 1 of delivery

The following must be in place on the Monday morning of Week 1. The 3-week plan has no Phase 0 buffer; pre-mobilisation must complete these before kick-off:

• [ ] App registration created (I1, I2)

• [ ] OIDC redirect URIs configured (I8)

• [ ] Entra ID groups created (I5)

• [ ] Service mailbox provisioned and Application Access Policy applied (M1, I6)

• [ ] Azure subscription + resource groups available (A1, A2)

• [ ] Key Vault provisioned (A5)

• [ ] Postgres provisioned (A4)

• [ ] App Service plan provisioned (A3)

• [ ] LLM provider chosen and procurement initiated (L1 series)

• [ ] CI/CD platform + repo created (T1, T2)

• [ ] Product Owner (P2) and IT Architecture liaison (P3) named and briefed

Items that can be in progress without blocking Day 1 (but must complete by the dates indicated):

• Conditional Access exemption (I7) — non-prod can sometimes bypass; prod cannot — needed by Day 13 (prod environment provisioning)

• Vendor master import (P12 / data) — needed by Day 14 (pilot cycle kick-off)

• Production DNS hostname + TLS cert (A8, A9) — needed by Day 14 (production cutover)

• Final brand sign-off on email templates (P13) — needed by Day 8 (Outlook email template build)

10. Open questions for Shell to answer

Does Shell IT Security accept certificate-based credentials for app-only auth (vs. client secret)? Assumed yes.

Does Shell IT Operations have an on-call rota for the workload after handover, or is it follow-the-sun support from Zensar in year 1?

Will Shell-side users connect to the app only from corporate devices, or also from BYOD? Affects Conditional Access policy choice.

Are there specific tagging or naming conventions for Azure resources we should adopt? We will follow Shell's IT Service Catalogue standard if provided.

Does Shell maintain a list of pre-approved 3rd-party LLM providers? If Anthropic is not pre-approved, that adds procurement time.

Is there a Shell-internal Wiki / Confluence space where this documentation and operational runbooks should live alongside the codebase docs?

Dependencies & Access — Zensar VendorPulse for Shell — 2026-06-03.