| CHANGE REQUEST |  |
| --- | --- |
| Part I – REQUEST |  |
| Reference Number: Shell Fleet Operations (L3/SRE Operations Team) | Date : |
| X X Change Requested By Shell Zensar | Prepared By : |

# Objective:

Shell currently runs vendor governance cycles (QBRs / EGBs) as a largely manual exercise, coordinators chase availability over email, scorecards arrive piecemeal across inboxes, alignment meetings recap the same recurring issues, and post-meeting minutes are inconsistent quarter on quarter. ZenVendorPulse is an agentic AI platform that automates the orchestration end-to-end while keeping every outbound action (emails, invites, briefs, minutes) under human approval. The proof-of-concept already demonstrates the six-stage workflow against a Gmail/Google-Forms-based mock environment. This document set scopes the work to lift that POC into a Shell-grade production deployment hosted in Shell's Azure tenant, integrated with Outlook + Teams, and removed entirely from Google's stack.

# 1 Scope/Capabilities Description

Deploy the already developed POC onto Shell's tenant delivering six vendor-governance capabilities:

| Capability | What it does |
| --- | --- |
| A: Meeting Scheduling & Coordination | Proposes and books EGB/QBR meetings via Graph, coordinating Shell and vendor attendees through the service mailbox. |
| B: Scorecard Input & Validation | Collects and validates 1-5 ratings across 4 categories / 16 parameters: Risk & Compliance, Performance, Commercial, Relationship. |
| C: Internal Alignment Calls Support | Prepares Shell-side alignment materials, consolidating scorecards and surfacing discussion points ahead of vendor engagement. |
| D: Vendor Prep Call Support | Drafts vendor pushbacks in three stances (Factual, Neutral, Escalation) under a legal-review guardrail. |
| E: EGB/QBR Combined Meeting Support | Runs the combined governance meeting, capturing decisions, actions and minutes for human approval. |
| F: Cross-Cycle Memory & Trend Analysis | Retains prior-cycle data to track vendor performance trends and recurring themes across governance cycles. |

# 2.  Features of the Agent

•  Deterministic-first, AI-second: LLM writes only human-readable text

•  Human-approval gate on every outbound action

•  12-state, forward-only workflow with full audit trail

•  Entra ID SSO with role-based access control (four roles)

•  Microsoft Graph app-only certificate auth for mail, calendar, Teams

•  All messaging from a single dedicated service mailbox

•  Native in-app scorecard form (1-5; 4 categories, 16 parameters)

•  Outlook-friendly email templates rendering on desktop, OWA, mobile

•  Provider-abstracted LLM: Anthropic Claude or Azure OpenAI, config-switchable

•  Full audit trail streamed to App Insights / Log Analytics

•  End-to-end observability across application and platform

•  Graph rate-limiting (429 handling) and LLM monthly token budgets

•  Graceful degradation when external services are unavailable

•  All secrets held in Azure Key Vault

•  Single-tenant deployment within Shell's Azure / Microsoft 365 estate

# 3. Out of Scope

•    No Shell-wide vendor-master, SAP Ariba or Coupa integration (pilot uses CSV/Excel  import)

- No contract-management capability

- No finance, spend or SAP integration

- No native mobile application (web-only)

- No multi-language support (English only)

- Performance/load testing at scale not yet conducted

- No third-party penetration testing completed

- No customer-managed keys (CMK) support

- No cross-region disaster recovery (DR)

- No SAP/Ariba integration

- No Teams transcript ingestion

- No Power Automate integration

# 4. High Level Timeline

Four working weeks (20 working days), sprint-paced: three weeks of development (Weeks 1-3) followed by a deployment and defect-warranty week (Week 4), with all Shell access pre-mobilised before Day 1.

| Phase | Duration | Key Outcome | Pre-Requisites/Ask from Shell |
| --- | --- | --- | --- |
| Pre-mobilisation | Before Day 1 | • Shell provisions Entra ID app registrations (NonProd + Prod) and admin consent on Graph application permissions • Service mailbox vendorpulse-svc@shell.com provisioned by Shell with Application Access Policy scoped to the app • Azure infrastructure provisioned by Shell — Postgres Flexible Server, Key Vault, App Service Plan, App Insights / Log Analytics, Container Registry, Front Door • LLM provider chosen and contract established by Shell (Anthropic or Azure OpenAI); API key deposited in Key Vault • DNS hostnames and TLS certificates provisioned by Shell for Prod and NonProd • Source repository and CI/CD pipeline provisioned by Shell with Zensar engineers added; service connection for deployment configured • Scorecard taxonomy drafted (locked at Day-2 checkpoint); 3 named UAT coordinators identified; one pilot vendor pre-agreed | Refer Section 6 — every item above is a Shell-side dependency that must be in place before Day 1 |
| Week 1 Foundations, Migration & Design Alignment | Days 1–5 | • Day 1 — Joint kick-off; pack walkthrough; day-zero prerequisites confirmed; ADRs locked; clean shell-prod branch with git-history scrub; CI lint + typecheck + unit tests on green • Day 2 (AM) — JSON-to-Postgres migration via Alembic; Key Vault integration via managed identity; pydantic-settings + azure-identity wired • Day 2 (PM) — Design Alignment Checkpoint with Shell VMO + IT Architecture + IT Security; 12 topics decided (incl. scorecard mode); Design Decision Log committed • Day 3 — MSAL OIDC end-user authentication + session cookie + role guards; Graph app-only certificate authentication working; Module B path validated by working spike • Day 4 — Gmail / Google Forms / google-auth code paths fully removed; non-prod App Service running containerised build via CI/CD pipeline • Day 5 — Module A end-to-end against real Graph (findMeetingTimes → event creation with Teams URL → invite via sendMail); Week 1 demo; design frozen Friday EoD | Day-2 attendees: Shell VMO Product Owner, IT Architecture liaison, IT Security liaison, Brand / Comms rep |
| Week 2 Development & Module Testing | Days 6–10 | • Day 6 — Module B core flow built in the chosen mode (in-app form OR Excel attachment per Day-2 decision); end-to-end stakeholder round-trip exercised • Day 7 — Module B completion (validation + reminder cadence + submission tracker); Modules C, D and F ported from POC with audit writes to external_calls • Day 8 — Module E live (live capture + transcript parsing + minutes generation); Outlook-friendly email templates redesigned and cross-client tested (desktop / OWA / mobile) • Day 9 — Admin module complete (vendor master, roles view, LLM budget panel, audit log viewer, system health); Shell branding applied across UI and emails • Day 10 — Hardening pass (per-cycle token budget, rate-limit middleware, error mapping, correlation IDs); full-cycle demo end-to-end; code freeze declared | Brand sign-off on email templates by Day 8; Module B path decision honoured through code freeze |
| Week 3 Hardening, Stabilisation & UAT | Days 11–15 | • Day 11 — UAT kick-off with 3 named Shell VMO coordinators; defect tracker established with P1/P2/P3 triage; observability finalisation begins • Day 12 — UAT day 2; P1 defects deployed same-day; App Insights operator workbook live; alert rules configured (app down, agent failure rate, Graph auth failure, LLM budget) • Day 13 — UAT day 3 with defect batch; regression test pass against full cycle; runbook v0.9 drafted (daily-ops checklist, P1/P2/P3 procedures, common-symptom reference) • Day 14 — Final UAT day; runbook walkthrough rehearsal with Shell IT Operations; pre-cutover health checks; on-call escalation routing tested • Day 15 — Release candidate baked, tagged and signed off; UAT defect log closed (P1/P2 fixed; P3 deferred to warranty); end-of-Week-3 review with Shell sponsor — NO GO-LIVE THIS WEEK | 3 named Shell VMO coordinators available for UAT (Days 11–15); Shell IT Operations available for runbook walkthrough on Day 14 |
| Week 4 Deployment, Pilot Go-Live & Warranty Start | Days 16–20 | • Day 16 — Bicep deployment to production resource group; Alembic migrations applied to prod Postgres; infrastructure smoke tests (App Service ↔ Postgres ↔ Key Vault); Shell IT Security final permissions review • Day 17 — Release-candidate image tagged prod-<date>-<sha> and deployed to prod slot:staging; smoke tests against staging slot; Shell IT Security formal sign-off; CAB ticket filed with runbook attached • Day 18 — CAB approval; DNS cutover (Shell DNS → Front Door endpoint); zero-downtime slot swap (production ← staging); 60-min observation window; pilot vendor cycle kick-off • Day 19 — Pilot cycle progresses through Module A → Module B; Zensar Tech Lead pair-shadowing the lead Shell VMO coordinator; App Insights monitored live; daily check-in • Day 20 — Pilot cycle continues; handover artefacts finalised (runbook v1.0, decision log, architecture pack); coordinator training session #1 delivered and recorded; end-of-engagement retro; defect-warranty period begins Monday Week 5 | Shell IT Security sign-off (Day 17), Shell CAB approval (Day 18), pilot-vendor cycle pre-agreed, coordinator availability for training (Day 20) |

# 5. Assumptions

•  Shell provides all pre-mobilization access, hardware & software before Day 1; no Phase-0 buffer.

•  Zensar team 100% allocated through the four development weeks (Weeks 1-4); deployment and warranty support in Week 4, with all the accesses and Licenses.

•  Pilot comprises a single vendor cycle.

•  POC functional behaviour accepted as baseline; only integration and platform re-engineered.

•  English-only, web-only, single-tenant delivery.

•  All attendees reside within or are invitable from Shell M365.

•  LLM provider chosen and contracted before Day 1.

•  Scorecard taxonomy locked at the Day-2 design checkpoint.

•  Shell names three UAT coordinators and pre-agrees one pilot vendor.

•  Design frozen at the end of Week 1.

# 6. Dependencies

The four-week plan assumes Shell provisions all items below before Day 1; any gap blocks the dependent capability and risks the schedule.

|  | Category | Items |
| --- | --- | --- |
|  | Shell Identity / Entra | - 2 app registrations (NonProd and Prod) - Certificate credentials for each app registration - Graph application-permission admin consent for the following permissions: - Mail.Send - Calendars.ReadWrite - OnlineMeetings.ReadWrite.All - User.Read.All - MailboxSettings.Read - Group.Read.All - Mail.Read / Mail.ReadWrite (if email-reply scorecard is enabled) - OIDC client configuration with redirect URIs - Entra security groups for 4 app roles - Exchange Application Access Policy scoping the service mailbox - Conditional Access exemption for the service principal |
| 2 | Microsoft 365 messaging & calendar | - Service mailbox (e.g. vendorpulse-svc@shell.com) with E3/E5 licence - Mailbox storage and retention policy configuration - Teams meeting policy for the service mailbox - External/guest meeting policy for vendor attendees - Litmus / Email-on-Acid for email-render QA |
| 3 | Azure infrastructure | - Azure subscription with deploy access - Resource groups for environment separation - App Service Plan (P1v3 for prod / B2 for nonprod) - PostgreSQL Flexible Server with HA for prod - Key Vault for secrets management - Front Door with WAF (Web Application Firewall) - App Insights and Log Analytics for monitoring - DNS/CNAME configuration with TLS certificate - Private endpoints and VNet integration - Managed Identity role assignments - Outbound NAT/egress allow-listing to Graph and LLM endpoints - Azure Policy and tagging compliance enforcement |
| 4 | LLM provider | - Anthropic enterprise account with DPA (zero-retention / no-training / EU compliance) - Anthropic API key stored in Key Vault - Monthly token budget configured for Anthropic account - OR Azure OpenAI quota with GPT-4o-class chat deployment - Azure OpenAI key stored in Key Vault |
| 5 | Shell delivery tooling | - Developer laptops with full local dev setup (Python 3.11+, Node.js, Docker, Git) and admin rights - Approved IDE (VS Code or JetBrains) with extensions - Claude Code / Claude for Work licences and Anthropic API developer key - Source-control and CI/CD (Azure DevOps or GitHub Enterprise) with branch protection and CI/CD service principal - Azure Container Registry - Static analysis tool (SonarQube) - Secret scanning (TruffleHog / GitLeaks) - Container scanning (Trivy / Snyk) - Dependabot / Renovate for dependency management - Litmus / Email-on-Acid for email testing - Optional Playwright / BrowserStack for automated browser testing - Network access, VPN and device-compliance to reach Shell tenant, repo and non-prod Graph |

# 7. Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Developer laptops not provided | Engineers cannot start; schedule slips | Shell confirms devices with admin rights pre-Day 1 |
| VS Code / IDE not approved | Development blocked | Pre-approve VS Code or JetBrains in pre-mobilisation |
| Claude Code / Anthropic licences not procured | Loss of AI-accelerated velocity; four-week plan slips | Secure licences and developer API key before Day 1 |
| Graph app-only admin consent late | Modules A and B blocked | Lodge consent early, track in pre-mobilisation |
| Graph throttling (429) | Mail/calendar operations fail intermittently | Implement retry with back-off and request batching |
| Conditional Access blocks service principal | Service mailbox actions fail | Agree service-principal CA exemption with Entra admin |
| External-attendee policy blocks vendor invites | Vendor meetings cannot be scheduled | Confirm external/guest meeting policy pre-Day 1 |
| LLM contract / DPA / residency not signed | Cannot process real data | Begin DPA early , track to closure |
| Azure OpenAI deployment misconfigured | LLM calls fail | Validate gpt-4o deployment and key during Week 1 |
| No SQL schema; messy POC data needs cleansing | Migration delays; data quality issues | Define schema and cleanse data in Week 1 migration |
| Scorecard taxonomy not locked | Form and schema rework | Lock 4-category/16-parameter taxonomy at Day-2 checkpoint |
| Scorecard form-platform decision late | Module B rework | Confirm scorecard mode before Week 2 build |
| Day-2 design checkpoint overload | Week-1 buffer exhausted; re-baseline | Pre-circulate design; freeze decisions end of Week 1 |
| Post-freeze scope change | Schedule and code-freeze breach | Enforce change control after Friday code freeze |
| Major UAT defect past its Week-4 slot | Go-live at risk | Prioritise P1/P2 fixes; security sign-off in Week 4 |
| Outlook email-rendering issues found late | Templates display incorrectly to vendors | Render-test early via Litmus/Email-on-Acid in Week 2 |
| Team-member unplanned absence | Capacity loss under no-PTO assumption | Confirm 100% allocation; hold contingency cover plan |
| Late security objection | Go-live blocked | Engage IT Security early; schedule Week-4 security sign-off |
| DNS/TLS cutover failure in Week 4 | Production cutover blocked | Pre-stage DNS/CNAME and TLS cert; rehearse cutover |
| LLM token-spend overrun | Budget exceeded | Set monthly token budget; monitor usage via App Insights |
| PII / data-residency / audit-retention sign-off | Cannot store vendor names and scorecard comments | Secure Legal/Privacy sign-off on retention pre-Day 1 |
| No automated tests today | Quality risk under compressed timeline | Add targeted tests; static/secret/container scanning in CI |

# 8. Acceptance Criteria

•  Production system live in Shell's Azure tenant.

•  Entra ID SSO login works; RBAC enforced across four app roles.

•  All six agents (A-F) functional.

•  Gmail, Google Forms and the delegated .env token fully removed.

•  Mail, calendar and Teams operate via Graph app-only from the service mailbox.

•  Scorecard collection working in the chosen mode.

•  Outlook email renders correctly on desktop, OWA and mobile.

•  Admin and audit modules complete.

•  Shell branding applied throughout.

•  One pilot vendor cycle progressing without P1 issues.

•  All P1/P2 UAT defects closed.

•  Security sign-off obtained.

•  Runbook v1.0 handed to Shell IT Operations.

•  Coordinator training delivered and recorded.

•  Documentation and decision log committed.

The 4-week defect warranty begins at handover, with end dates agreed at that point.

| Part II – RESPONSE TO REQUEST |  |
| --- | --- |
| Date : 4/11/2025 |  |
| Response By Customer X X Zensar | Prepared By : Vinish Pillai |
| New changes starting from November ’25 Onwards 6.3 Year 2 [Nov 25 to Feb 26] Payment Details: Sr No /Month; Payment Milestone; Milestone Date; Amount (INR). 9 – 12; Provision of Services for Month X of Year 2; 1st Week of Month X+1; INR 10,44,000. Data Entry for Manual Vouchers -From 1st November 2025 to 28th February 2026 Cumulative Charges over the Contract period. Year 2(November 2025 to February 2026 ) Monthly; Total Charges ( November 2025 to February 2026 ) Yearly. Charges; INR 10,44,000; INR 41,76,000. |
| This CR changes are related to SOW against Shell Managed L2/L3 Services for Emerald MTSP project dated 10-July -2025 |  |
| Vinish Pillai Name and Signature of Authorized Representative of Responding Party Astrid Robb |  |